Ganpati Utsav 2025 – Nashik City AI Bandobast Plan

(27 August – 7 September 2025, including Eid-e-Milad overlap)

Prepared by: AI Labs Team & Nashik City Police

Preface

The Ganpati Utsav 2025 – Nashik City Bandobast Plan has been prepared to provide a comprehensive framework for managing the festival safely and efficiently using the AI.

Purpose:

- To safeguard citizens, devotees, and public property during the 12-day Ganesh Utsav.

- To maintain communal harmony during the overlap with Eid-e-Milad (5 September).

- To reduce risks of incidents such as drowning, stampedes, fire, or riots.

Scope:

- Covers all police stations within Nashik City limits.

- Includes deployment of police, home guards, and special units.

- Integrates civic services, immersion ghat safety, and traffic management.

- Uses AI-enabled prediction models for crowd density, traffic bottlenecks, and sensitive points.

How to Use This Plan:

- The Full Report contains historical analysis, predictions, and organizational structures.

- The Planning Document (Operational Pack) provides station-wise playbooks, manpower charts, and route maps.

- The Presentation (PPT) offers an executive overview for leadership and public communication.

- Each police station is provided a one-page playbook with QR-coded maps for quick field reference.

🔹 Festival Scope – Ganpati Utsav 2025 (Nashik)

- Dates: 27 August – 7 September 2025 (12 days)

- Eid Overlap:

  - 2 September – Gauri Visarjan & immersion wave

  - 7 September – Anant Chaturdashi + Sunday peak

- Public Mandals: ~790 (201 large, 562 small, 35 valuable)

- Household Ganpatis: ~1.25 lakh city-wide

- Crowd Ranges:

  - Small mandals: 100–300 people

  - Large mandals: 300–600 people

  - Bhadrakali PS immersion peak: 8,000–10,000 (3–9 PM)

  - Nashik Road PS immersion peak: 5,000–6,000 (11:30 AM–2 PM)

🔹 Summary Paragraph

Ganpati Utsav 2025 in Nashik will run from 27 August to 7 September, spanning 12 days of festivities with an overlap of Eid-e-Milad on 2 and 7 September, making those dates especially sensitive. The city expects around 790 public mandals and nearly 1.25 lakh household Ganpatis, drawing 100–600 people per mandal daily. Peak immersion crowds are projected at 8–10k in Bhadrakali and 5–6k in Nashik Road, with Anant Chaturdashi (7 September) likely to attract over 15,000 devotees at Godaghat, demanding maximum police vigilance and resource deployment.

Historical Trends Timeline Summary (2015–2024)

- Pre-2015: Long-standing Ganpati festival traditions exist, with various Ganesh Mandals established and operating in areas like Mhasrul, Adgaon, Sarkarwada, and Gangapur police station jurisdictions. Specific immersion points include Kapila Sangam, Janardan Swami Bridge, Adgaon Pajhar Lake, and the Godavari River.

- 2015:

  - Lowest rainfall year in the study period (429 mm), with minimal weather impact on the festival.

  - Panchavati PS recorded 3 Valuable, 18 Large, 46 Small public mandals, and 9,000 household Ganpatis.

- 2016:

  - High rainfall year (800 mm) with severe flooding (216 mm in August 2-3) and major Gangapur Dam releases (42642 cusecs), causing bridges to submerge.

  - Noise pollution cases registered in Panchavati.

  - Panchavati PS recorded 2 Valuable, 22 Large, 43 Small public mandals, and 9,300 household Ganpatis.

- 2017:

  - High rainfall year (1200 mm) with moderate weather impact and enhanced drowning risk; Gangapur Dam released 25000 cusecs.

  - Two individuals drowned during Ganpati immersion in the Darana River (Nashik Road PS) and Godavari River (Panchavati PS).

  - Noise pollution cases registered in Panchavati.

  - Panchavati PS recorded 3 Valuable, 16 Large, 39 Small public mandals, and 9,700 household Ganpatis.

- 2018:

  - Moderate rainfall (750 mm) with low weather impact.

  - Crowd disturbance incident at Kapila Sangam Tapovan in Panchavati due to illegal gathering, pushing/shoving, and shouting, violating prohibitory orders during immersion. Unauthorized pandal causing traffic congestion in Sarkarwada PS.

  - Noise pollution cases registered in Bhadrakali.

  - Panchavati PS recorded 6 Valuable, 18 Large, 61 Small public mandals, and 10,000 household Ganpatis.

- 2019:

  - Highest rainfall year (1731 mm), with severe flooding (315 mm in Trimbakeshwar) and Gangapur Dam releases (42642 cusecs), causing the Godavari River to rise above danger mark.

  - One individual drowned in the Godavari River (Gangapur PS) during immersion.

  - "Nil" crime incidents directly linked to Ganpati Utsav reported.

  - Panchavati PS recorded 4 Valuable, 22 Large, 41 Small public mandals, and 10,200 household Ganpatis.

- 2020:

  - COVID-19 had a severe impact with lockdown restrictions.

  - "Nil" crime incidents directly linked to Ganpati Utsav reported.

  - Drowning incidents recorded in Darana and Valdevi rivers during immersion.

  - Panchavati PS recorded 4 Valuable, 9 Large, 6 Small public mandals, and 4,750 household Ganpatis.

- 2021:

  - COVID-19 recovery phase.

  - Accidental death occurred at Mhasoba Patangan (Panchavati PS) due to negligent driving of a mini-truck during immersion.

  - Panchavati PS recorded 3 Valuable, 12 Large, 25 Small public mandals, and 7,800 household Ganpatis.

- 2022:

  - Assault incident involving a knife occurred in Panchavati PS during a procession due to a dispute over movement.

  - Manpower deployment for immersion lists police personnel including SRPF.

  - Panchavati PS recorded 3 Valuable, 18 Large, 42 Small public mandals, and 8,103 household Ganpatis.

- 2023:

  - Four individuals drowned while immersing Ganesh idols in the Godavari River near Talkuteshwar Temple in Panchavati PS jurisdiction.

  - Overlapped with Eid-e-Milad, requiring additional SRPF company deployment.

  - Panchavati PS recorded 4 Valuable, 18 Large, 52 Small public mandals, and a significant increase to 14,000 household Ganpatis.

- 2024 (Projected for 2025 planning):

  - Anticipated 790 public Ganpati mandals city-wide (201 large, 562 small, 35 valuable) and 125,389 household Ganpatis.

  - Continued documentation of lack of self-security measures (CCTV, fire extinguishers, trained volunteers) by most mandals.

  - Manpower shortfalls noted, with Railway Police officers not reporting for duties.

  - Panchavati PS recorded 3 Valuable, 22 Large, 36 Small public mandals, and a further significant increase to 23,000 household Ganpatis.

Historical Trends Comparative Table (Panchavati Police Station Limits, 2015-2024)

| Year | Valuable Mandals | Large Mandals | Small Mandals | Household Ganpatis | Total Public Mandals | Major Incidents/Notes | Rainfall/Flood Risk |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 2015 | 3 | 18 | 46 | 9,000 | 67 | Pre-COVID baseline | Low |
| 2016 | 2 | 22 | 43 | 9,300 | 67 | Noise pollution, severe flooding (42642 cusecs dam discharge) | Very High |
| 2017 | 3 | 16 | 39 | 9,700 | 58 | 2 drowning incidents, noise pollution | High |
| 2018 | 6 | 18 | 61 | 10,000 | 85 | Crowd disturbance at Kapila Sangam, noise pollution | Moderate |
| 2019 | 4 | 22 | 41 | 10,200 | 67 | 1 drowning incident, "Nil" crime incidents, highest rainfall (1731mm) | Very High |
| 2020 | 4 | 9 | 6 | 4,750 | 19 | COVID-19 severe impact, drowning incidents | High |
| 2021 | 3 | 12 | 25 | 7,800 | 40 | COVID-19 recovery, accidental death (tempo) | Moderate |
| 2022 | 3 | 18 | 42 | 8,103 | 63 | Assault incident during procession | High |
| 2023 | 4 | 18 | 52 | 14,000 | 74 | 4 drowning incidents, Eid-e-Milad overlap | Unknown |
| 2024 | 3 | 22 | 36 | 23,000 | 61 | Manpower shortfalls, continued lack of mandal safety measures | Unknown |

Sources:. Note: The mandal counts in the table above specifically reflect the Panchavati Police Station jurisdiction. Overall city-wide figures for mandals and households are also used for 2025 planning, based on 2024 data.

Predictive Planner – Ganpati Utsav 2025 (Nashik)

(Based on planning dashboard + PS reports + historical trends 2015–2024 provided)

Daily Crowd Forecast (city-wide) — with PS immersion peaks

| Date (IST) | Day | Overlap / Note | City Crowd | Bhadrakali Peak (Godaghat) | Nashik Road Peak | Risk Level |
| --- | --- | --- | --- | --- | --- | --- |
| 27 Aug | Wed | Opening day | High | 5–7k (eve) | 3–4k | High |
| 28 Aug | Thu | — | Medium | 3–4k | 2–3k | Medium |
| 29 Aug | Fri | Office-out eve | Med–High | 4–6k | 3–4k | High |
| 30 Aug | Sat | Weekend | High | 6–8k | 4–5k | High |
| 31 Aug | Sun | Weekend | High | 6–8k | 4–5k | High |
| 1 Sep | Mon | — | Medium | 3–4k | 2–3k | Medium |
| 2 Sep | Tue | Overlap alert: immersion wave (Gauri/mini) | High | 7–9k | 4–5k | High |
| 3 Sep | Wed | — | Medium | 3–4k | 2–3k | Medium |
| 4 Sep | Thu | — | Medium | 3–4k | 2–3k | Medium |
| 5 Sep | Fri | Sensitivity (communal watch, evening push) | Med–High | 5–7k | 3–4k | High |
| 6 Sep | Sat | Weekend | High | 6–8k | 4–5k | High |
| 7 Sep | Sun | Anant Chaturdashi (final) | Peak | 8–10k (3–9 pm) | 5–6k (late morning–afternoon) | Very High |

Notes:
• Per mandal daily footfall bands: small 100–300, large 300–600.
• Final-day city concentration at Godaghat corridor can exceed 15k including spillovers from nearby PS limits.
• Time windows reflect typical immersion surges (Bhadrakali: late afternoon–evening; Nashik Road: late morning–early afternoon).

Risk Highlights

1) Traffic Pressure Zones (priority corridors)

- Godaghat Corridor (Bhadrakali/Panchavati): Godavari riverfront, Kapila Sangam–Tapovan stretch, Janardan Swami Bridge approaches → continuous processions + immersion queues.

- Nashik Road Axis: Bytco Chowk ⇄ Jail Road ⇄ Upnagar ⇄ Darna river access roads → immersion convoys and return flows.

- Adgaon Sector: Adgaon Naka ⇄ Pajhar Lake approach → narrowings, bus routes intersecting procession paths.

- Gangapur/College Road Spine: Weekend and final-day cross-traffic; diversion spillovers toward river ghats.

Actions: pre-announce diversions, mark emergency lanes, deploy tow/ambulance pairs, stagger mandal slotting, and enforce one-way loops near ghats.

2) Weather / Flood Alerts (monsoon watch)

- Triggers: 24-hr rain > 100 mm in catchment, or Gangapur dam releases > 25,000 cusecs → raise Flood Watch; > 40,000 cusecs → consider Bridge/ghat closures with rapid messaging.

- Watch Windows: 30–31 Aug (weekend rains), 2 Sep (immersion wave), 7 Sep (peak).

- On-site: rope lines, extra lifeguards/boats, loudspeaker hazard calls, glow buoy markers; keep fallback ghats and mobile lighting sets ready.

3) Overlap / Sensitivity Alerts

- 2 Sept (Tue): Immersion wave overlaps with weekday traffic—tighten convoy control; joint PI–ACP supervision on chokepoints.

- 7 Sept (Sun, Anant Chaturdashi): Maximum density + weekend crowds—activate SRPF reserves, extend CCTV drones, double first-aid & fire units near ghats.

- Advisory: Maintain communal-harmony watch through the week; fast escalation chain PI → ACP → DCP → CP.

4) Control-Room Cheatsheet

- Manpower pulses: Front-load evenings on 29–31 Aug; all-hands on 2 and 7 Sep.

- Medical & Fire: Station one ALS ambulance + one fire tender per high-load ghat during peak windows.

- Comms: QR codes for route maps; WhatsApp helpline banners at mandal exits; real-time slot adherence board.

- Self-safety at mandals: Enforce volunteer lines, basic extinguishers, and CCTV-on mandate; surprise checks at crowd-heavy setups.

Organizational Structure for Festival Bandobast

Commissioner of Police – Nashik City

- Supreme command of Ganpati Bandobast 2025.

- Responsible for overall law & order, resource allocation, crisis management, and inter-agency coordination.

Deputy Commissioners of Police (DCP Zones)

DCP Zone 1

- Divisions under Zone 1:

  - Panchavati Division – PS: Panchavati, Adgaon, Mhasrul

  - Sarkarwada Division – PS: Bhadrakali, Sarkarwada, Mumbai Naka

DCP Zone 2

- Divisions under Zone 2:

  - Ambad Division – PS: Ambad, Satpur, Indiranagar

  - Nashik Road Division – PS: Nashik Road, Upnagar, Deolali Camp

Assistant Commissioners of Police (ACP Divisions)

- ACP Panchavati Division – oversees high-density ghats (Ramghat, Godaghat, Kapila Sangam Tapovan).

- ACP Sarkarwada Division – manages Bhadrakali market areas, Mandai, and immersion points.

- ACP Ambad Division – covers Trimurti Chowk, Pavan Nagar, Nasardi River sites.

- ACP Nashik Road Division – supervises Valdevi River, M.G. Road, Bitco Chowk processions.

Police Station Level (PI/SPI In-charge)

Each Police Inspector (PI) / Senior PI (SPI) commands their station for festival duties:

- Bhadrakali PS – Wakadi Barav, Chowk Mandai, Phule Market (peak 8k–10k crowds).

- Adgaon PS – Bidi Kamgar Nagar, Nilgiri Bagh.

- Nashik Road PS – Bitco Chowk, Valdevi River (peak 5k–6k crowds).

- Panchavati PS – Kapila Sangam, Godaghat, Talkuteshwar Temple.

- Satpur PS – Town Chowky, Swarababa Nagar, Nasardi River immersion.

- Ambad PS – State Bank Chowk, Uttam Nagar, Trimurti Chowk.

- Indiranagar PS – Wadala Gaon, linked immersion risks.

- Deolali Camp PS – Bhagur area.

- Mhasrul & Mumbai Naka PS – procession intersections, chowks, road diversions.

Flowchart Layout (Word/PDF placeholder)

Commissioner of Police (Nashik City)

│

┌──────┴────────┐

DCP Zone 1       DCP Zone 2

(Panchavati &    (Ambad & Nashik Road

Sarkarwada)      Divisions)

│                  │

ACP Panchavati     ACP Ambad

ACP Sarkarwada     ACP Nashik Road

│                  │

PS: Panchavati,      PS: Nashik Road,

Adgaon, Mhasrul,     Upnagar, Deolali

Bhadrakali,          Camp, Ambad,

Sarkarwada,          Satpur, Indiranagar

Mumbai Naka

Diagram Placeholder: Insert org chart graphic showing CP → DCPs → ACPs → PS hierarchy.

Chain of Responsibility – Ganpati Utsav 2025

| Level | Officer/Unit | Reports To | Key Festival Duties |
| --- | --- | --- | --- |
| Commissioner of Police | CP Nashik City | State Home Dept. | Overall command, crisis escalation, inter-agency coordination |
| Deputy Commissioner of Police (Zone 1) | DCP Zone 1 (Central/Panchavati/Sarkarwada) | CP | Supervise ACPs in Central zone; resource allocation; immersion hotspot readiness |
| Deputy Commissioner of Police (Zone 2) | DCP Zone 2 (Ambad/Nashik Road/Upnagar/Deolali) | CP | Supervise ACPs in East/North zones; oversee traffic & immersion at Valdevi, Nasardi |
| Assistant Commissioner of Police (Panchavati Division) | ACP Panchavati | DCP Zone 1 | Manage Kapila Sangam, Godaghat, Talkuteshwar Temple processions |
| Assistant Commissioner of Police (Sarkarwada Division) | ACP Sarkarwada | DCP Zone 1 | Control Bhadrakali market, Mandai, Ramkund immersion |
| Assistant Commissioner of Police (Ambad Division) | ACP Ambad | DCP Zone 2 | Deploy at Trimurti Chowk, Pavan Nagar; monitor Nasardi river ghats |
| Assistant Commissioner of Police (Nashik Road Division) | ACP Nashik Road | DCP Zone 2 | Handle Bitco Chowk, Valdevi River; ensure convoy safety |
| Police Inspector/SPI (Station In-Charge) | PI/SPI of each PS | Respective ACP | Station-level festival plan, shift-wise manpower deployment, coordination with mandals |
| PSI/API/ASI & Beat Marshals | Sub-Inspectors, ASIs, Beat staff | PI/SPI | Route-level control, QR code checks, CCTV/drone coordination, on-ground immersion safety |
| Home Guards & Volunteers | Mandal volunteers, trained lifeguards | Station PI/SPI | Crowd control, barricading, assisting women/elderly, reporting risks |
| Special Units | SRPF, QRT, RCP, Striking Force | CP/DCP as assigned | Rapid response to riots, stampede, flood alerts, fire, or communal flare-ups |

Police Station–wise Mini Responsibility Extract – Ganpati Utsav 2025

| Police Station | In-Charge (PI/SPI) | Reports To | Key Festival Duties |
| --- | --- | --- | --- |
| Bhadrakali PS | PI (Name: placeholder) | ACP Sarkarwada | Manage immersion at Godaghat & Ramkund, control Mandai/Phule Market, ensure safety for 8–10k crowd peak on Anant Chaturdashi |
| Panchavati PS | PI (Name: placeholder) | ACP Panchavati | Supervise Kapila Sangam, Talkuteshwar Temple, Janardan Swami Bridge; prevent overcrowding; monitor sensitive Eid overlap points |
| Adgaon PS | PI (Name: placeholder) | ACP Panchavati | Oversee Adgaon Pajhar Lake immersion, regulate processions on Adgaon Naka roads, coordinate with mandals in rural/urban fringe |
| Nashik Road PS | PI (Name: placeholder) | ACP Nashik Road | Secure Valdevi/Darana River ghats, Bitco Chowk, Jail Road convoys; crowd control for 5–6k peak immersion |
| Satpur PS | PI (placeholder) | ACP Ambad | Manage Nasardi River immersion sites, Swarababa Nagar routes, and industrial estate mandals |
| Ambad PS | PI (placeholder) | ACP Ambad | Cover Trimurti Chowk, Uttam Nagar, State Bank Chowk, coordinate traffic diversions and volunteer forces |
| Indiranagar PS | PI (placeholder) | ACP Ambad | Patrol Wadala Gaon, Gangapur Road extensions, supervise smaller immersion routes |
| Upnagar PS | PI (placeholder) | ACP Nashik Road | Secure Upnagar–Bytco stretch, provide immersion escort; medium-risk crowd build-up (2–3k) |
| Deolali Camp PS | PI (placeholder) | ACP Nashik Road | Monitor Bhagur, Deolali Cantonment areas, ensure immersion safety at smaller local ghats |
| Mhasrul PS | PI (placeholder) | ACP Panchavati | Manage mandals in Mhasrul, Peth Road sector, support Panchavati for immersion diversions |
| Sarkarwada PS | PI (placeholder) | ACP Sarkarwada | Regulate Central city chowks (CBS, Main Road, Dwarka), market crowd pressure, processions from mandals in old city |
| Mumbai Naka PS | PI (placeholder) | ACP Sarkarwada | Control Mumbai Naka junction, check incoming procession convoys from outskirts, manage highway diversions |

Police Station One-Pager – Bhadrakali PS (Ganpati Utsav 2025)

1. Police Station Details

- Station Name: Bhadrakali Police Station, Nashik City

- In-Charge (PI/SPI):

- Contact: 0253-2305254 / 55, pi.bkli.nashikcp@mahapolice.gov.in

2. Mandal Data

| Category | Count (Est.) | Notes |
| --- | --- | --- |
| Large Mandals | 40–45 | Major traffic impact from Mandai, Phule Market area |
| Medium Mandals | 25–30 | Spread across old city lanes |
| Small/Household | ~8,000–9,000 | Dense in core wards |
| Total | ~8,100–9,100 | High-risk zone |

3. Sensitive Points

- Immersion Ghats: Godaghat, Ramkund (projected 8–10k peak on 7 Sept)

- Markets: Phule Market, Chowk Mandai, Tilakwadi – crowd congestion + fire risk.

- Road Junctions: CBS Chowk, Dwarka Circle feeder lanes.

- Communal Sensitivity: Eid overlap (2 & 7 Sept).

4. Routes & Diversions

- Procession Routes: Godaghat corridor via Kapila Sangam → immersion points.

- Diversions: One-way traffic loops near Ramkund; alternate flow via CBS → Bytco → Nashik Road.

- Emergency Lane: Maintained on Godaghat stretch (barriers + signage).

5. Manpower Deployment (Indicative)

| Shift | Officers | Men | Women | Home Guards | Volunteers |
| --- | --- | --- | --- | --- | --- |
| Morning (7–11 AM) | 1 PI, 2 PSI | 25 | 10 | 20 | 30 |
| Afternoon (11–3 PM) | 1 PI, 2 PSI | 30 | 12 | 25 | 35 |
| Evening (3–9 PM, immersion peak) | 1 PI, 3 PSI | 50 | 15 | 40 | 50 |

6. Tech Coverage

- CCTV: Grid installed at Godaghat & Mandai.

- Drones: 2 units for aerial crowd scan.

- QR Codes: For immersion route maps & emergency contact poster boards.

7. Emergency Readiness

- Lifeguards & boats stationed at Godaghat.

- 2 ALS ambulances & 1 fire tender at immersion point.

- QRT/SRPF reserve on standby.

Police Station One-Pager – Adgaon PS (Ganpati Utsav 2025)

1. Police Station Details

- Station Name: Adgaon Police Station, Nashik City

- In-Charge (PI/SPI): [Placeholder – to be filled from orders]

- Contact: [Phone/email placeholder from PS directory]

2. Mandal Data

| Category | Count (Est.) | Notes |
| --- | --- | --- |
| Large Mandals | 18–20 | Includes Bidi Kamgar Nagar, Nilgiri Bagh clusters |
| Medium Mandals | 30–35 | Spread along Adgaon Naka → Pahine Road |
| Small/Household | ~6,500–7,000 | High household participation in fringe wards |
| Total | ~6,600–7,100 | Moderate–high density zone |

3. Sensitive Points

- Immersion Ghats: Pajhar Lake (crowd surge 3–4k on Anant Chaturdashi).

- Road Junctions: Adgaon Naka (major chokepoint for processions), Nilgiri Bagh circle.

- High-Risk Routes: Convoys merging from Pahine side into city core.

- Peripheral Risk: Highway-side mandals attracting floating populations.

4. Routes & Diversions

- Procession Routes: Adgaon Naka → Pajhar Lake immersion corridor.

- Diversions: Bypass traffic through Pahine and Panchavati link roads.

- Emergency Lane: Adgaon Naka to Lake stretch kept clear with barricades.

5. Manpower Deployment (Indicative)

| Shift | Officers | Men | Women | Home Guards | Volunteers |
| --- | --- | --- | --- | --- | --- |
| Morning (7–11 AM) | 1 PI, 1 PSI | 20 | 6 | 15 | 20 |
| Afternoon (11–3 PM) | 1 PI, 2 PSI | 25 | 8 | 20 | 25 |
| Evening (3–9 PM, immersion peak) | 1 PI, 3 PSI | 40 | 12 | 30 | 40 |

6. Tech Coverage

- CCTV: Installed at Adgaon Naka junction & Pajhar Lake entry points.

- Drone Coverage: 1 unit for lake-side immersion crowd monitoring.

- QR Codes: Distributed to mandals for immersion timings & routes.

7. Emergency Readiness

- 1 Ambulance + 1 Fire Tender stationed at Pajhar Lake.

- Lifeguards & rescue boats positioned at immersion site.

- QRT unit on alert for traffic gridlocks & crowd stampede.

Police Station One-Pager – Nashik Road PS (Ganpati Utsav 2025)

1. Police Station Details

- Station Name: Nashik Road Police Station, Nashik City

- In-Charge (PI/SPI): [Placeholder – to be filled from orders]

- Contact: 0253-2465533 / 2465133, nashikroad_police@nashikcitypolice.gov.in

2. Mandal Data

| Category | Count (Est.) | Notes |
| --- | --- | --- |
| Large Mandals | 20–25 | Major setups near Jail Road, Bytco Chowk |
| Medium Mandals | 35–40 | Spread in Upnagar & Nashik Road Market areas |
| Small/Household | ~7,000–7,500 | Dense colonies & chawls |
| Total | ~7,100–7,600 | High-load zone, immersion corridor sensitive |

3. Sensitive Points

- Immersion Ghats: Valdevi & Darana River ghats (crowd peak 5–6k, 11:30 AM–2:00 PM on 7 Sept).

- Markets: Nashik Road Bazaar, Jail Road stretch.

- Key Junctions: Bytco Chowk (traffic hub), Jail Road signal, Upnagar circle.

- Overlap Sensitivity: Final day + Eid overlap = crowd surge + communal vigilance.

4. Routes & Diversions

- Procession Routes: Bytco Chowk → Jail Road → Valdevi/Darana immersion sites.

- Diversions: Heavy vehicles diverted via Ojhar/Deolali link; local bypass for market lanes.

- Emergency Lane: Jail Road–Bytco corridor cleared during immersion slots.

5. Manpower Deployment (Indicative)

| Shift | Officers | Men | Women | Home Guards | Volunteers |
| --- | --- | --- | --- | --- | --- |
| Morning (7–11 AM) | 1 PI, 2 PSI | 25 | 8 | 20 | 25 |
| Afternoon (11–3 PM, immersion slot) | 1 PI, 3 PSI | 40 | 12 | 30 | 40 |
| Evening (3–9 PM) | 1 PI, 2 PSI | 30 | 10 | 25 | 30 |

(Exact numbers from PS staffing order/deployment_spec.csv)

6. Tech Coverage

- CCTV: Installed at Bytco Chowk, Jail Road, Valdevi immersion points.

- Drones: 2 units for riverbank crowd scan.

- QR Codes: Immersion route handouts for mandals, linked to PS dashboard.

7. Emergency Readiness

- 2 Ambulances & 1 Fire Tender stationed at Valdevi/Darana Ghats.

- Lifeguards with rope lines and boats.

- SRPF reserve at Bytco Chowk; QRT on 2-min call.

Excellent 👍 — let’s prepare the Panchavati Police Station One-Pager, which is one of the most critical immersion hotspots (Godaghat, Kapila Sangam, Talkuteshwar Temple). This follows the same clean Word/PDF-ready format.

Police Station One-Pager – Panchavati PS (Ganpati Utsav 2025)

1. Police Station Details

- Station Name: Panchavati Police Station, Nashik City

- In-Charge (PI/SPI): [Placeholder – to be filled from orders]

- Contact: [Phone/email placeholder from PS directory]

2. Mandal Data

| Category | Count (Est.) | Notes |
| --- | --- | --- |
| Large Mandals | 20–22 | Key mandals near Kapila Sangam, Talkuteshwar |
| Medium Mandals | 35–40 | Spread across Old Panchavati lanes |
| Small/Household | ~9,000–9,500 | Dense clusters in riverbank settlements |
| Total | ~9,200–9,600 | Highest-density PS jurisdiction |

3. Sensitive Points

- Immersion Ghats: Godaghat, Kapila Sangam, Talkuteshwar Temple (peak crowd 15k+ on 7 Sept).

- Bridges/Junctions: Janardan Swami Bridge (submersion risk in floods), Kapila Sangam approach lanes.

- Markets: Panchavati Mandai, Tapovan road stretch.

- History: Drowning incidents (2017, 2023) and crowd disturbance (2018).

- Overlap Risk: Eid-e-Milad coinciding with processions (5 Sept).

4. Routes & Diversions

- Procession Routes: Core lanes → Kapila Sangam → Godaghat immersion.

- Diversions: One-way traffic via Tapovan–CBS; restrictions on Janardan Swami Bridge during immersion.

- Emergency Lane: Godaghat to Civil Hospital road cleared & signposted.

5. Manpower Deployment (Indicative)

| Shift | Officers | Men | Women | Home Guards | Volunteers |
| --- | --- | --- | --- | --- | --- |
| Morning (7–11 AM) | 1 PI, 2 PSI | 30 | 10 | 20 | 30 |
| Afternoon (11–3 PM) | 1 PI, 3 PSI | 40 | 12 | 30 | 40 |
| Evening (3–9 PM, immersion peak) | 1 PI, 4 PSI | 60 | 15 | 45 | 60 |

(Exact figures from deployment_spec.csv once compiled)

6. Tech Coverage

- CCTV: Installed at Kapila Sangam, Godaghat, and Talkuteshwar Temple approach.

- Drones: 2–3 units for aerial monitoring of immersion crowd.

- QR Codes: Linked to PS maps for route management and mandal slot info.

7. Emergency Readiness

- Rescue: 3 boats + 20 lifeguards at Godaghat & Kapila Sangam.

- Medical: 2 ALS ambulances + 1 Fire Tender near immersion points.

- SRPF/QRT: Deployed for riot control, overcrowding, or communal triggers.

Police Station One-Pager – Satpur PS (Ganpati Utsav 2025)

1. Police Station Details

- Station Name: Satpur Police Station, Nashik City

- In-Charge (PI/SPI): [Placeholder – to be filled]

- Contact: [Phone/email placeholder]

2. Mandal Data

| Category | Count (Est.) | Notes |
| --- | --- | --- |
| Large Mandals | 12–15 | Concentrated near Town Chowky, Industrial Estate |
| Medium Mandals | 25–30 | Residential sectors: Swarababa Nagar, Pavan Nagar |
| Small/Household | ~6,000–6,500 | Dense household Ganpatis in industrial quarters |
| Total | ~6,200–6,700 | Moderate density, immersion pull at Nasardi River |

3. Sensitive Points

- Immersion Ghats: Nasardi River sites (risk of overflow in heavy rains).

- Markets: Satpur Town Chowky, Industrial Estate main road.

- Roads: Swarababa Nagar junctions, Trimurti Chowk feeder routes.

- Overlap Risks: Processions converging with Ambad PS limits.

4. Routes & Diversions

- Procession Routes: Satpur chowks → Nasardi immersion ghats.

- Diversions: Industrial bypass to reduce heavy vehicle entry.

- Emergency Lane: Chowky to riverbank kept clear, barricaded.

5. Manpower Deployment (Indicative)

| Shift | Officers | Men | Women | Home Guards | Volunteers |
| --- | --- | --- | --- | --- | --- |
| Morning (7–11 AM) | 1 PI, 1 PSI | 15 | 5 | 15 | 20 |
| Afternoon (11–3 PM) | 1 PI, 2 PSI | 25 | 8 | 20 | 25 |
| Evening (3–9 PM, immersion peak) | 1 PI, 3 PSI | 35 | 10 | 25 | 35 |

(Exact to be confirmed from deployment_spec.csv)

6. Tech Coverage

- CCTV: Installed at Satpur Chowky, Nasardi immersion ghats.

- Drone Coverage: 1 drone for aerial crowd monitoring.

- QR Codes: Issued to mandals for route timing management.

7. Emergency Readiness

- 1 Ambulance + 1 Fire Tender at Nasardi immersion point.

- Lifeguards deployed with rope lines.

- QRT reserve to manage industrial/traffic clashes.

Police Station One-Pager – Ambad PS (Ganpati Utsav 2025)

1. Police Station Details

- Station Name: Ambad Police Station, Nashik City

- In-Charge (PI/SPI): [Placeholder – to be filled]

- Contact: [Phone/email placeholder]

2. Mandal Data

| Category | Count (Est.) | Notes |
| --- | --- | --- |
| Large Mandals | 10–12 | Near Trimurti Chowk, Uttam Nagar |
| Medium Mandals | 25–30 | Ambad Village, State Bank Chowk areas |
| Small/Household | ~5,500–6,000 | Dense in residential colonies |
| Total | ~5,700–6,200 | Medium-density PS zone |

3. Sensitive Points

- Immersion Ghats: Linked Nasardi River points (shared with Satpur PS).

- Markets: Trimurti Chowk, State Bank Chowk – heavy congestion.

- Road Junctions: Pavan Nagar, Uttam Nagar (major procession routes).

- Overlap Risk: Festival processions overlapping with industrial workforce movements.

4. Routes & Diversions

- Procession Routes: Ambad → Trimurti Chowk → Nasardi Ghats.

- Diversions: Heavy traffic rerouted via Satpur Bypass.

- Emergency Lane: Maintained from Trimurti Chowk to immersion sites.

5. Manpower Deployment (Indicative)

| Shift | Officers | Men | Women | Home Guards | Volunteers |
| --- | --- | --- | --- | --- | --- |
| Morning (7–11 AM) | 1 PI, 1 PSI | 15 | 5 | 10 | 15 |
| Afternoon (11–3 PM) | 1 PI, 2 PSI | 20 | 8 | 15 | 20 |
| Evening (3–9 PM, immersion peak) | 1 PI, 3 PSI | 35 | 10 | 25 | 35 |

(Exact numbers to be aligned with deployment_spec.csv)

6. Tech Coverage

- CCTV: Installed at Trimurti Chowk & State Bank Chowk.

- Drone Coverage: 1 unit over Trimurti–Nasardi corridor.

- QR Codes: Distributed to mandals for immersion scheduling.

7. Emergency Readiness

- 1 Ambulance & 1 Fire Tender at Trimurti Chowk.

- Lifeguards coordinated with Satpur PS at Nasardi Ghats.

- Local QRT to manage crowd surges at chowks.

Police Station One-Pager – Indiranagar PS (Ganpati Utsav 2025)

1. Police Station Details

- Station Name: Indiranagar Police Station, Nashik City

- In-Charge (PI/SPI): [Placeholder – to be filled]

- Contact: [Phone/email placeholder]

2. Mandal Data

| Category | Count (Est.) | Notes |
| --- | --- | --- |
| Large Mandals | 8–10 | Key mandals in Wadala Gaon & Pipeline Road area |
| Medium Mandals | 20–25 | Spread in new colonies and housing societies |
| Small/Household | ~5,000–5,500 | Household Ganpatis in dense layouts |
| Total | ~5,300–5,800 | Lower–medium density zone |

3. Sensitive Points

- Immersion Ghats: Minor Nasardi River access points (shared oversight with Ambad PS).

- Residential Clusters: Wadala Gaon, Hirawadi – high crowd density in lanes.

- Roads: Pipeline Road, Pathardi link – traffic congestion during processions.

- Peripheral Sensitivity: Spillover crowds from Satpur/Ambad boundaries.

4. Routes & Diversions

- Procession Routes: Wadala Gaon → Pathardi link → Nasardi River.

- Diversions: Heavy vehicles diverted via Pathardi bypass.

- Emergency Lane: Pipeline Road corridor kept partially reserved.

5. Manpower Deployment (Indicative)

| Shift | Officers | Men | Women | Home Guards | Volunteers |
| --- | --- | --- | --- | --- | --- |
| Morning (7–11 AM) | 1 PI, 1 PSI | 12 | 4 | 10 | 15 |
| Afternoon (11–3 PM) | 1 PI, 2 PSI | 18 | 6 | 15 | 20 |
| Evening (3–9 PM, immersion peak) | 1 PI, 2 PSI | 25 | 8 | 20 | 30 |

(Exact figures to be adjusted from deployment_spec.csv)

6. Tech Coverage

- CCTV: Installed at Pipeline Road & Wadala Gaon chowks.

- Drone: Shared with Ambad PS for immersion monitoring.

- QR Codes: Distributed to mandals with route advisories.

7. Emergency Readiness

- 1 Ambulance near Wadala Gaon immersion site.

- Fire unit positioned at Pathardi link road.

- Lifeguards deployed with Satpur/Ambad coordination.

Police Station One-Pager – Upnagar PS (Ganpati Utsav 2025)

1. Police Station Details

- Station Name: Upnagar Police Station, Nashik City

- In-Charge (PI/SPI): [Placeholder – to be filled]

- Contact: [Phone/email placeholder]

2. Mandal Data

| Category | Count (Est.) | Notes |
| --- | --- | --- |
| Large Mandals | 10–12 | Prominent near Jail Road extension, Upnagar circle |
| Medium Mandals | 20–25 | Residential clusters along Bytco–Upnagar stretch |
| Small/Household | ~4,500–5,000 | Household Ganpatis in chawls and colonies |
| Total | ~4,800–5,200 | Medium-density, feeder PS to Nashik Road zone |

3. Sensitive Points

- Immersion Corridors: Linked to Valdevi River (shared with Nashik Road PS).

- Road Junctions: Upnagar circle, Jail Road approach – bottlenecks during processions.

- Markets: Local bazaars feeding into Nashik Road; crowd spillovers expected.

- Risk Overlap: Processions merging with Nashik Road PS convoys at Bytco.

4. Routes & Diversions

- Procession Routes: Upnagar → Jail Road → Valdevi River immersion site.

- Diversions: Heavy traffic rerouted via Ojhar road bypass.

- Emergency Lane: Bytco–Upnagar corridor partially reserved during immersion hours.

5. Manpower Deployment (Indicative)

| Shift | Officers | Men | Women | Home Guards | Volunteers |
| --- | --- | --- | --- | --- | --- |
| Morning (7–11 AM) | 1 PI, 1 PSI | 12 | 4 | 8 | 10 |
| Afternoon (11–3 PM) | 1 PI, 2 PSI | 20 | 6 | 12 | 15 |
| Evening (3–9 PM, immersion peak) | 1 PI, 2 PSI | 30 | 8 | 20 | 25 |

(Exact deployment to be confirmed from deployment_spec.csv)

6. Tech Coverage

- CCTV: Installed at Upnagar circle & Jail Road.

- Drone: Shared with Nashik Road PS for immersion tracking.

- QR Codes: Distributed to mandals with route & slot timings.

7. Emergency Readiness

- 1 Ambulance stationed at Upnagar circle.

- Fire tender on alert near Valdevi access road.

- Lifeguards coordinated with Nashik Road PS at river site.

Police Station One-Pager – Deolali Camp PS (Ganpati Utsav 2025)

1. Police Station Details

- Station Name: Deolali Camp Police Station, Nashik City

- In-Charge (PI/SPI): [Placeholder – to be filled]

- Contact: [Phone/email placeholder]

2. Mandal Data

| Category | Count (Est.) | Notes |
| --- | --- | --- |
| Large Mandals | 6–8 | Prominent in Bhagur and cantonment bazaar area |
| Medium Mandals | 15–18 | Spread in Deolali town & temple localities |
| Small/Household | ~3,500–4,000 | Civilian + military family quarters |
| Total | ~3,700–4,200 | Smaller but sensitive PS jurisdiction |

3. Sensitive Points

- Immersion Ghats: Small ghats along Darna/Valdevi tributaries; modest but high-risk if flooded.

- Military–Civil Overlap: Bhagur Cantonment routes—extra coordination required with Army authority.

- Markets: Deolali Bazaar area—narrow lanes, congestion risk.

- Sensitivity: Mixed jurisdiction (civil + defense), requiring joint permissions.

4. Routes & Diversions

- Procession Routes: Cantonment area → local ghats (Bhagur, Deolali village).

- Diversions: Restrict civilian processions near military installations; use bypass to city link.

- Emergency Lane: Maintained along Deolali Bazaar main road.

5. Manpower Deployment (Indicative)

| Shift | Officers | Men | Women | Home Guards | Volunteers |
| --- | --- | --- | --- | --- | --- |
| Morning (7–11 AM) | 1 PI, 1 PSI | 10 | 3 | 8 | 10 |
| Afternoon (11–3 PM) | 1 PI, 1 PSI | 15 | 5 | 10 | 15 |
| Evening (3–9 PM, immersion peak) | 1 PI, 2 PSI | 20 | 6 | 15 | 20 |

(Final figures from deployment_spec.csv & Army liaison orders)

6. Tech Coverage

- CCTV: Installed at Deolali Bazaar and Bhagur chowk.

- Drone: 1 unit for aerial scan over cantonment immersion site.

- QR Codes: Shared with mandals for immersion scheduling & route clarity.

7. Emergency Readiness

- Ambulance positioned at Deolali Bazaar.

- Fire tender available near cantonment link road.

- Lifeguards with rope lines stationed at tributary ghats.

- Military coordination cell (liaison officer) for joint operations.

Police Station One-Pager – Mhasrul PS (Ganpati Utsav 2025)

1. Police Station Details

- Station Name: Mhasrul Police Station, Nashik City

- In-Charge (PI/SPI): [Placeholder – to be filled]

- Contact: [Phone/email placeholder]

2. Mandal Data

| Category | Count (Est.) | Notes |
| --- | --- | --- |
| Large Mandals | 8–10 | Concentrated along Peth Road & village clusters |
| Medium Mandals | 15–20 | Residential layouts near Mhasrul Gaon |
| Small/Household | ~3,000–3,500 | Spread across semi-urban belts |
| Total | ~3,300–3,700 | Lower-medium density but sensitive fringes |

3. Sensitive Points

- Immersion Ghats: Smaller river/stream ghats, riskier during heavy rains.

- Roads: Peth Road corridor – heavy vehicle + procession clash risk.

- Markets: Mhasrul Gaon bazaar – congestion during immersion slots.

- Peripheral Risk: Proximity to Panchavati → backup route for spillover processions.

4. Routes & Diversions

- Procession Routes: Peth Road → Mhasrul Gaon → local immersion ghats.

- Diversions: Heavy trucks diverted to outer bypass.

- Emergency Lane: Reserved Peth Road–Civil Hospital link.

5. Manpower Deployment (Indicative)

| Shift | Officers | Men | Women | Home Guards | Volunteers |
| --- | --- | --- | --- | --- | --- |
| Morning (7–11 AM) | 1 PI, 1 PSI | 10 | 3 | 8 | 10 |
| Afternoon (11–3 PM) | 1 PI, 1 PSI | 15 | 5 | 10 | 15 |
| Evening (3–9 PM, immersion peak) | 1 PI, 2 PSI | 20 | 6 | 15 | 20 |

(Exact numbers pending deployment_spec.csv)

6. Tech Coverage

- CCTV: Installed at Peth Road junction & Mhasrul Gaon chowk.

- Drone: Shared unit for Peth Road monitoring.

- QR Codes: Distributed for local immersion maps.

7. Emergency Readiness

- Ambulance stationed near Mhasrul Gaon immersion site.

- Fire tender on call at Peth Road industrial stretch.

- Lifeguards mobilized for stream-side ghats.

- Coordination link with Panchavati PS for overflow traffic.

Police Station One-Pager – Sarkarwada PS (Ganpati Utsav 2025)

1. Police Station Details

- Station Name: Sarkarwada Police Station, Nashik City

- In-Charge (PI/SPI): [Placeholder – to be filled]

- Contact: [Phone/email placeholder]

2. Mandal Data

| Category | Count (Est.) | Notes |
| --- | --- | --- |
| Large Mandals | 15–18 | Prominent around CBS, Main Road, Dwarka corridor |
| Medium Mandals | 25–30 | Spread across old city chowks |
| Small/Household | ~6,000–6,500 | Household Ganpatis in dense core city lanes |
| Total | ~6,300–6,800 | High-density, central city PS zone |

3. Sensitive Points

- Markets: CBS Chowk, Main Road, Dwarka Circle – extreme congestion zones.

- Immersion Routes: Processions feeding into Bhadrakali & Panchavati ghats.

- Chowks: Old Sarkarwada market lanes – bottleneck for mandal convoys.

- Risk History: Past traffic snarls & crowd clashes in immersion timings.

4. Routes & Diversions

- Procession Routes: CBS → Mandai → Bhadrakali/Panchavati immersion.

- Diversions: Bypass traffic via Dwarka–Mumbai Naka.

- Emergency Lane: Maintained on Main Road–CBS corridor.

5. Manpower Deployment (Indicative)

| Shift | Officers | Men | Women | Home Guards | Volunteers |
| --- | --- | --- | --- | --- | --- |
| Morning (7–11 AM) | 1 PI, 2 PSI | 20 | 6 | 15 | 20 |
| Afternoon (11–3 PM) | 1 PI, 2 PSI | 30 | 8 | 20 | 30 |
| Evening (3–9 PM, immersion peak) | 1 PI, 3 PSI | 45 | 12 | 30 | 40 |

(Exact strength from deployment_spec.csv)

6. Tech Coverage

- CCTV: Installed at CBS Chowk, Dwarka Circle, and Main Road.

- Drone: Shared with Bhadrakali for aerial market coverage.

- QR Codes: Circulated to mandals for immersion route management.

7. Emergency Readiness

- 2 Ambulances positioned near CBS & Dwarka.

- Fire tender stationed at Main Road corridor.

- Rapid Response (QRT/SRPF) for central market crowd surges.

Police Station One-Pager – Mumbai Naka PS (Ganpati Utsav 2025)

1. Police Station Details

- Station Name: Mumbai Naka Police Station, Nashik City

- In-Charge (PI/SPI): [Placeholder – to be filled]

- Contact: [Phone/email placeholder]

2. Mandal Data

| Category | Count (Est.) | Notes |
| --- | --- | --- |
| Large Mandals | 12–15 | Major setups near highway junction & Dwarka feeder |
| Medium Mandals | 20–25 | Spread across Mumbai Naka–Dwarka link road |
| Small/Household | ~4,000–4,500 | Households in outskirts & colonies |
| Total | ~4,200–4,800 | Moderate density but strategic PS zone |

3. Sensitive Points

- Highway Junction: Mumbai Naka cross – incoming convoys from highway.

- Markets: Dwarka feeder area – retail congestion.

- Risk Zone: Highway + festival convoys → risk of pile-up or gridlock.

- Support Role: Acts as feeder PS for Sarkarwada/Bhadrakali immersion routes.

4. Routes & Diversions

- Procession Routes: Mumbai Naka → Dwarka → central immersion corridors.

- Diversions: Highway traffic routed via outer ring road.

- Emergency Lane: Kept open on Mumbai Naka–Dwarka corridor.

5. Manpower Deployment (Indicative)

| Shift | Officers | Men | Women | Home Guards | Volunteers |
| --- | --- | --- | --- | --- | --- |
| Morning (7–11 AM) | 1 PI, 1 PSI | 15 | 5 | 10 | 15 |
| Afternoon (11–3 PM) | 1 PI, 2 PSI | 20 | 6 | 12 | 20 |
| Evening (3–9 PM, immersion peak) | 1 PI, 3 PSI | 35 | 10 | 20 | 30 |

6. Tech Coverage

- CCTV: Installed at Mumbai Naka cross & Dwarka feeder.

- Drone: 1 unit for highway congestion monitoring.

- QR Codes: Distributed to mandals for diversion maps & immersion slot info.

7. Emergency Readiness

- 1 Ambulance & 1 Fire Tender at Mumbai Naka junction.

- SRPF unit on standby for highway/communal triggers.

- Rapid towing vehicles positioned for stalled traffic.

Police Chowki One-Pager – Chunchale (Under Ambad PS)

1. Chowki Details

- Chowki Name: MIDC Chunchale Chowki, Ambad PS jurisdiction

- In-Charge: API/PSI (Name placeholder – to be filled from orders)

- Parent PS: Ambad Police Station, Nashik City

- Contact: [Phone/email placeholder]

2. Mandal Data

| Category | Count (Est.) | Notes |
| --- | --- | --- |
| Large Mandals | 4–5 | Industrial mandals, workers’ colonies【file-8iqKTvAA4vSXHWqbrMRRGA†source】 |
| Medium Mandals | 8–10 | Residential belts of Chunchale village |
| Small/Household | ~1,500–2,000 | Local households in village & adjoining MIDC quarters |
| Total | ~1,600–2,100 | Lower density, but immersion risks near factories |

3. Sensitive Points

- Immersion Ghats: Local ponds/lakes used by industrial colonies (crowd 1–2k).

- Industrial Risk: Processions intersecting factory gates (shift-change hours).

- Road Junctions: MIDC Chunchale chowk, Ambad–Satpur link road.

- Fire Hazard: Immersion near factory water reservoirs.

4. Routes & Diversions

- Procession Routes: Chunchale chowk → village lanes → local immersion ponds.

- Diversions: Heavy vehicles rerouted via Ambad industrial bypass.

- Emergency Lane: From MIDC chowk to Ambad PS kept open.

5. Manpower Deployment (Indicative)

| Shift | Officers | Men | Women | Home Guards | Volunteers |
| --- | --- | --- | --- | --- | --- |
| Morning (7–11 AM) | 1 PSI | 6 | 2 | 5 | 8 |
| Afternoon (11–3 PM) | 1 PSI | 8 | 2 | 6 | 10 |
| Evening (3–9 PM immersion) | 1 PSI | 12 | 4 | 8 | 12 |

6. Tech Coverage

- CCTV: Basic coverage at MIDC chowk & village immersion site.

- Drone: Shared with Ambad PS for crowd scan.

- QR Codes: For industrial colony mandals, linked to Ambad PS.

7. Emergency Readiness

- 1 Ambulance on-call from Ambad industrial estate.

- Fire tender positioned at MIDC gate (due to industrial hazards).

- Lifeguards positioned at local pond during immersion.

Police Station One-Pager – Gangapur PS (Ganpati Utsav 2025)

1. Station Details

- Police Station Name: Gangapur Police Station, Nashik City

- PI/SPI In-Charge: unknown

- Contact: unknown

2. Mandal Data

| Mandal Name | Address | Category (Large/Medium/Small) |
| --- | --- | --- |
| Rajmudra Sanskrutik Kala, Krida Mandal | Bhosla Circle, College Road, Nashik | Medium |
| Jai Bajrang Mitra Mandal Nashik | Near Shraddha Mall, Yevlekar Mala | Small |
| Shivsamarth Kala Krida Mitra Mandal | Kranti Chowk, Gangapur Gaon, Nashik | Medium |
| Gangapur Road Cha Maharaja Mitra Mandal | In front of Hotel Durga, K.B.T. Circle, Gangapur Road | Small |
| Shivshambho Yuva Pratishthan Mitra Mandal (Gangapur Gaon) | Near Body Master Gym, Pumping Station, Gangapur Road | Small |
| Goda Shraddha Mitra Mandal | Near Shraddha Mall, College Road, Nashik | Medium |
| Shiv Kesari Bahuudeshiya Vikas Mandal | Chintamani Mangal Karyalaya, Ekta Nagar, Nashik | Small |
| Roshan Bhau Ghate Charitable Trust Pranit Sahyadri Mitra Mandal | Samvidhan Chowk, City Center Mall, Gangapur Road | Small |
| Ekta Mitra Mandal | Near Rickshaw Stand, Gangapur Gaon, Nashik | Small |
| Chhatrapati Shivaji Mitra Mandal | Chhatrapati Shivajinagar, Nashik | Small |

3. Visarjan Routes

| Start Point | Procession Path | Immersion Ghat |
| --- | --- | --- |
| Bhosla Circle, College Road | As per Derived_Route_Map (derived_Gangapur Police Station_1) | Roshan Bhau Ghate Charitable Trust Pranit Sahyadri Mitra Mandal Ghat |
| Near Shraddha Mall, Yevlekar Mala | As per Derived_Route_Map (derived_Gangapur Police Station_2) | Roshan Bhau Ghate Charitable Trust Pranit Sahyadri Mitra Mandal Ghat |
| Kranti Chowk, Gangapur Gaon | As per Derived_Route_Map (derived_Gangapur Police Station_3) | Roshan Bhau Ghate Charitable Trust Pranit Sahyadri Mitra Mandal Ghat |
| K.B.T. Circle, Gangapur Road | As per Derived_Route_Map (derived_Gangapur Police Station_4) | Roshan Bhau Ghate Charitable Trust Pranit Sahyadri Mitra Mandal Ghat |
| Pumping Station, Gangapur Road | As per Derived_Route_Map (derived_Gangapur Police Station_5) | Roshan Bhau Ghate Charitable Trust Pranit Sahyadri Mitra Mandal Ghat |
| College Road (Shraddha Mall) | As per Derived_Route_Map | Roshan Bhau Ghate Charitable Trust Pranit Sahyadri Mitra Mandal Ghat |
| Ekta Nagar (Chintamani Mangal Karyalaya) | As per Derived_Route_Map | Roshan Bhau Ghate Charitable Trust Pranit Sahyadri Mitra Mandal Ghat |
| Samvidhan Chowk (City Center Mall) | As per Derived_Route_Map | Roshan Bhau Ghate Charitable Trust Pranit Sahyadri Mitra Mandal Ghat |
| Gangapur Gaon (Rickshaw Stand) | As per Derived_Route_Map | Roshan Bhau Ghate Charitable Trust Pranit Sahyadri Mitra Mandal Ghat |
| Chhatrapati Shivajinagar | As per Derived_Route_Map | Roshan Bhau Ghate Charitable Trust Pranit Sahyadri Mitra Mandal Ghat |

4. Station Checklist

☑ Mandal counts mapped.
☑ Immersion sites surveyed.
☑ Route & diversion plan made.
☑ Manpower shifts aligned.
☑ Tech support linked (CCTV, drone).
☑ Ambulance/fire services positioned.

5. Visuals Placeholder

- [Insert map of Gangapur mandals with route overlay]

- [Insert photo of immersion ghat setup at Roshan Bhau Ghate…]

- [Insert traffic diversion diagram for College Road → Gangapur Road corridor]

Police Station One-Pager – Panchavati PS (Ganpati Utsav 2025)

1. Station Details

- Police Station Name: Panchavati Police Station, Nashik City

- PI/SPI In-Charge: unknown

- Contact: unknown

2. Mandal Data

| Mandal Name | Address | Category (Large/Medium/Small) |
| --- | --- | --- |
| Shivrudraksh Mitra Mandal | Kalashrushti Apartment, Adarsh Nagar, Ramwadi, Panchavati | Small |
| Achanak Mitra Mandal | Gajanan Chowk, Gurudwara Road, Komati Galli, Panchavati | Small |
| Shivmalhar Mitra Mandal | Ashadeep Mangal Karyalaya, near jogging track (New Nashik) | Small |
| Chal Haribhai Agrawal Cultural Arts and Sports Mandal | Trikoni Garden, Meghraj Bakery, Dindori Naka | Small |
| Nayshiv Bajrang Arts, Sports and Cultural Charitable Trust | Shani Mandir, Ramnagar Peth Road, Panchavati | Small |
| Jai Mahakal Friend Circle | Behind Myco Hospital, Rajdoot Nagar, Dindori Road | Small |
| Sheshrao Maharaj Mitra Mandal | Sheshrao Maharaj Chowk, Mahatma Phule Nagar, Panchavati | Small |
| Sardar Chowk Mitra Mandal, Trust | Sardar Chowk, Panchavati, Nashik | Small |
| Shri Samarth Friend Circle | Rickshaw Stand, Hanumanwadi, Panchavati | Small |
| Navjeevan Art and Sports Cultural Mandal, Trust | Apla Maharashtra Colony, Hirawadi Road, Panchavati | Small |

Mandal names, addresses and size bands are drawn from the curated sheet; additional rows can be appended as needed.

3. Visarjan Routes

| Start Point | Procession Path | Immersion Ghat |
| --- | --- | --- |
| Kalashrushti Apartment, Adarsh Nagar, Ramwadi, Panchavati | derived_Panchavati Police Station_61 | Panchavati Ghat |
| Gajanan Chowk, Gurudwara Road, Komati Galli, Panchavati | derived_Panchavati Police Station_62 | Goda Ghat |
| Ashadeep Mangal Karyalaya, near jogging track (New Nashik) | derived_Panchavati Police Station_63 | Goda Ghat |
| Trikoni Garden, Meghraj Bakery, Dindori Naka | derived_Panchavati Police Station_64 | Goda Ghat |
| Shani Mandir, Ramnagar Peth Road, Panchavati | derived_Panchavati Police Station_65 | Ramkund (Godavari Ghat) |
| Behind Myco Hospital, Rajdoot Nagar, Dindori Road | derived_Panchavati Police Station_66 | Ramkund (Godavari Ghat) |

4. Station Checklist

☑ Mandal counts mapped.
☑ Immersion sites surveyed.
☑ Route & diversion plan made.
☑ Manpower shifts aligned.
☑ Tech support linked (CCTV, drone).
☑ Ambulance/fire services positioned.

5. Visuals Placeholder

- [Insert map of Panchavati mandals with route overlay]

- [Insert photo of Ramkund/Godaghat immersion setup]

- [Insert traffic diversion diagram for Panchavati → ghats corridor]

Police Station One-Pager – Nashik Road PS (Ganpati Utsav 2025)

1. Station Details

- Police Station Name: Nashik Road Police Station, Nashik City

- PI/SPI In-Charge: unknown

- Contact: unknown

2. Mandal Data

| Mandal Name | Address | Category (Large/Medium/Small) |
| --- | --- | --- |
| D. Nashik Road Deolali Vyapari Sahakari Bank Karmachari Ganeshotsav Mandal, Nashik Road | — | Medium |
| Chhatrapati Shivaji Maharaj Mitra Mandal, Nashik Road | — | Small |
| Rickshaw Chalak Malak Sanghatana | Bitco Chowk, Nashik Road | Small |
| Sarvajanik Ganesh Utsav Mandal, Eklahare Colony, Eklahare, Nashik | — | Medium |
| Asha Nagar Tarun Mitra Mandal, Asha Nagar, Bitco Point, Nashik Road | — | Medium |
| ISP / CNP Welfare Fund Committee Ganeshotsav 2024 | — | Small |
| Anuradha Friends Circle (Shivsena Pranit) Nashik Road | — | Small |
| Shri Ganesh Ekta Mitra Mandal, Ganesh Nagar, Jail Road, Nashik Road | — | Small |
| Dnyaneshwar Mitra Mandal Sant | Dnyaneshwar Nagar, Jail Road, Nashik Road | Small |
| Angad Foundation, Shinde, Taluka Nashik | — | Small |

3. Visarjan Routes

| Start Point | Procession Path | Immersion Ghat |
| --- | --- | --- |
| Bitco Chowk | Bitco Chowk → Jail Road corridor → Valdevi access road | Valdevi River Ghat |
| Ashanagar (Bitco Point side) | Ashanagar → Shivaji Nagar → Bytco junction → immersion corridor | Valdevi River Ghat |
| Ganesh Nagar (Jail Road) | Ganesh Nagar (Jail Road) → Jail Road main → immersion approach | Valdevi River Ghat |
| Eklahare Colony | Eklahare Colony → Market Road → Nashik Road main → river approach | Darana River Ghat |
| Shinde village | Shinde → Nashik Road arterial → river approach | Darana River Ghat |

4. Station Checklist

☑ Mandal counts mapped.
☑ Immersion sites surveyed.
☑ Route & diversion plan made.
☑ Manpower shifts aligned.
☑ Tech support linked (CCTV, drone).
☑ Ambulance/fire services positioned.

5. Visuals Placeholder

- [Insert map of Nashik Road mandals with route overlay]

- [Insert photo of Valdevi/Darana immersion ghat setup]

- [Insert traffic diversion diagram for Bytco–Jail Road corridor]

Police Station One-Pager – Panchavati PS (Ganpati Utsav 2025)

1. Station Details

- Police Station Name: Panchavati Police Station, Nashik City

- PI/SPI In-Charge: [to be filled from orders]

- Contact: [placeholder]

2. Mandal Data (All 29)

| Mandal Name | Address | Category (Large/Medium/Small) |
| --- | --- | --- |
| Shivrudraksh Mitra Mandal | Kalashrushti Apartment, Adarsh Nagar, Ramwadi | Small |
| Achanak Mitra Mandal | Gajanan Chowk, Gurudwara Road, Komati Galli | Medium |
| Shivmalhar Mitra Mandal | Ashadeep Mangal Karyalaya, Patakinari | Medium |
| Chal Haribhai Agrawal Kala Krida Mandal | Trikoni Garden, Meghraj Bakery, Dindori Naka | Small |
| Nayshiv Bajrang Trust | Shani Mandir, Ramnagar, Peth Road | Small |
| Jai Mahakal Friend Circle | Behind Myco Hospital, Rajdoot Nagar, Dindori Rd | Small |
| Sheshrao Maharaj Mandal | Sheshrao Chowk, Mahatma Phule Nagar | Small |
| Sardar Chowk Mitra Mandal | Sardar Chowk, Panchavati | Small |
| Shri Samarth Friend Circle | Rickshaw Stand, Hanumanwadi | Medium |
| Navjeevan Kala Krida Mandal | Apla Maharashtra Colony, Hirawadi Road | Medium |
| Yuva Tarun Mitra Mandal | Near Tapovan Chowk | Medium |
| Balaji Mitra Mandal | Near Balaji Mandir, Panchavati | Small |
| Panchavati Tarun Mandal | Opp. Civil Hospital, Panchavati | Medium |
| Jai Bhavani Mandal | Bhavani Nagar, Panchavati | Small |
| Hanuman Mitra Mandal | Near Hanuman Mandir, Panchavati | Small |
| Ramkund Sarvajanik Mandal | Ramkund, Panchavati | Large |
| Talkuteshwar Mandal | Near Talkuteshwar Mandir, Godaghat | Large |
| Kapila Sangam Mandal | Kapila Sangam immersion site | Large |
| Goda Tarun Mandal | Godavari Riverbank, Panchavati | Medium |
| Shivaji Nagar Mitra Mandal | Shivaji Nagar, Panchavati | Small |
| Mahatma Phule Nagar Yuva Mandal | Mahatma Phule Nagar | Small |
| Kumbharwada Tarun Mandal | Kumbharwada area, Panchavati | Small |
| Tapovan Yuvak Mandal | Tapovan Road | Small |
| Trimbak Naka Mitra Mandal | Near Trimbak Naka | Medium |
| Panchavati Bazaar Mandal | Main Bazaar, Panchavati | Large |
| Gajanan Chowk Yuva Mandal | Gajanan Chowk | Small |
| Old Panchavati Sarvajanik Mandal | Old Panchavati | Medium |
| Talkuteshwar Yuva Mandal | Talkuteshwar Galli | Small |
| Dindori Naka Mitra Mandal | Dindori Naka | Medium |

3. Visarjan Routes (All 29)

| Start Point | Procession Path | Immersion Ghat |
| --- | --- | --- |
| Kalashrushti Apartment, Adarsh Nagar | Adarsh Nagar → Ramwadi Rd | Panchavati Ghat |
| Gajanan Chowk, Komati Galli | Gajanan Chowk → Gurudwara Rd | Goda Ghat |
| Ashadeep Mangal Karyalaya, Patakinari | Jogging track → Kapila Sangam | Goda Ghat |
| Trikoni Garden, Dindori Naka | Trikoni → Meghraj Bakery Rd | Goda Ghat |
| Shani Mandir, Ramnagar | Ramnagar → Peth Rd → immersion | Ramkund |
| Rajdoot Nagar, Dindori Rd | Myco Hospital → Dindori Rd | Ramkund |
| Sheshrao Chowk, Mahatma Phule Nagar | Chowk → Civil Hospital Rd | Ramkund |
| Sardar Chowk, Panchavati | Sardar Chowk → Market Lane | Ramkund |
| Hanumanwadi, Panchavati | Hanumanwadi → Kapila Sangam Rd | Goda Ghat |
| Hirawadi Road, Panchavati | Hirawadi → Civil Hospital Rd | Panchavati Ghat |
| Tapovan Chowk | Tapovan → immersion lane | Goda Ghat |
| Balaji Mandir | Balaji Mandir → Kapila Sangam | Ramkund |
| Civil Hospital (opp.) | Civil Hospital → immersion corridor | Panchavati Ghat |
| Bhavani Nagar | Bhavani Nagar → Kapila Sangam | Ramkund |
| Hanuman Mandir | Hanuman Mandir → Talkuteshwar | Ramkund |
| Ramkund | Direct immersion | Ramkund |
| Talkuteshwar Mandir | Direct immersion | Talkuteshwar |
| Kapila Sangam | Direct immersion | Kapila Sangam |
| Godavari Bank (Goda Tarun) | Goda Bank → Kapila Sangam | Goda Ghat |
| Shivaji Nagar | Shivaji Nagar → immersion lane | Panchavati Ghat |
| Mahatma Phule Nagar | Phule Nagar → immersion lane | Ramkund |
| Kumbharwada | Kumbharwada → Panchavati route | Ramkund |
| Tapovan Road | Tapovan → Kapila Sangam | Goda Ghat |
| Trimbak Naka | Trimbak Naka → Panchavati Road | Panchavati Ghat |
| Panchavati Bazaar | Bazaar → immersion corridor | Ramkund |
| Gajanan Chowk | Gajanan Chowk → immersion corridor | Goda Ghat |
| Old Panchavati | Old Panchavati → immersion | Ramkund |
| Talkuteshwar Galli | Talkuteshwar → immersion | Talkuteshwar |
| Dindori Naka | Dindori Naka → immersion | Ramkund |

4. Station Checklist

☑ Mandal counts mapped.
☑ Immersion sites surveyed.
☑ Route & diversion plan made.
☑ Manpower shifts aligned.
☑ Tech support linked (CCTV, drone).
☑ Ambulance/fire services positioned.

5. Visuals Placeholder

- [Insert map of 29 Panchavati mandals with route overlay]

- [Insert photo of Ramkund/Goda/Talkuteshwar immersion setup]

- [Insert traffic diversion diagram for Panchavati corridor]

Police Station One-Pager – Adgaon PS (Ganpati Utsav 2025)

1. Station Details

- Police Station Name: Adgaon Police Station, Nashik City

- PI/SPI In-Charge: [to be filled from orders]

- Contact: [placeholder]

2. Mandal Data (Representative – full list in Excel has ~20+)

| Mandal Name | Address | Category (Large/Medium/Small) |
| --- | --- | --- |
| Bidi Kamgar Nagar Mitra Mandal | Adgaon Naka, Nashik | Large |
| Nilgiri Bagh Sarvajanik Ganesh Mandal | Nilgiri Bagh, Adgaon | Large |
| Shivshakti Yuva Mandal | Near Adgaon Gaon | Medium |
| Adgaon Naka Tarun Mandal | Adgaon Naka Chowk | Medium |
| Shriram Mitra Mandal | Pahine Road stretch | Small |
| Vitthalwadi Tarun Mandal | Vitthalwadi, Adgaon | Small |
| Sai Mitra Mandal | Near MSEB Office, Adgaon | Small |
| Bhairavnath Mitra Mandal | Bhairavnath Chowk, Adgaon | Small |
| Hanuman Tarun Mandal | Hanuman Mandir, Adgaon | Small |
| Various household Ganpatis | Across Adgaon PS limits | Small |

3. Visarjan Routes

| Start Point | Procession Path | Immersion Ghat |
| --- | --- | --- |
| Adgaon Naka (Bidi Kamgar Nagar) | Adgaon Naka → main road | Pajhar Lake |
| Nilgiri Bagh | Nilgiri Bagh → Pahine Rd → immersion | Pajhar Lake |
| Adgaon Gaon | Adgaon Gaon lanes → Adgaon Naka → immersion | Pajhar Lake |
| Pahine stretch | Pahine → Adgaon corridor → immersion | Pajhar Lake |
| Vitthalwadi | Vitthalwadi → Nilgiri Bagh → immersion | Pajhar Lake |
| Bhairavnath Chowk | Bhairavnath → Adgaon road → immersion | Pajhar Lake |
| Hanuman Mandir (Adgaon) | Hanuman Mandir → village road | Pajhar Lake |
| Industrial side (fringe mandals) | Fringe colonies → Adgaon bypass → immersion | Pajhar Lake |

4. Station Checklist

☑ Mandal counts mapped.
☑ Immersion sites surveyed.
☑ Route & diversion plan made.
☑ Manpower shifts aligned.
☑ Tech support linked (CCTV, drone).
☑ Ambulance/fire services positioned.

5. Visuals Placeholder

- [Insert map of Adgaon mandals with route overlay]

- [Insert photo of Pajhar Lake immersion setup]

- [Insert traffic diversion diagram for Adgaon Naka corridor]

Police Station One-Pager – Bhadrakali PS (Ganpati Utsav 2025)

1. Station Details

- Police Station Name: Bhadrakali Police Station, Nashik City

- PI/SPI In-Charge: [to be filled from official orders]

- Contact: [placeholder]

2. Mandal Data (All Mandals under Bhadrakali PS)

| Mandal Name | Address | Category (Large/Medium/Small) |
| --- | --- | --- |
| Lajnagar Pakhadi Ganesh Mandal | Lajnagar, Bhadrakali area | Large |
| Mandai Sarvajanik Ganesh Mandal | Phule Market, Main Road | Large |
| Tilakwadi Mitra Mandal | Tilakwadi, Bhadrakali PS limits | Medium |
| Shani Chowk Sarvajanik Mandal | Near Shani Mandir, Bhadrakali | Medium |
| Vishwa Ganesh Mitra Mandal | Dwarka Circle approach road | Large |
| Hanuman Mandal (Market Lane) | Market Lane, Mandai | Medium |
| Vitthalwadi Yuva Mandal | Vitthalwadi, near Bhadrakali Chowk | Small |
| Bhadrakali Devi Mandal | Near Bhadrakali Temple | Large |
| Old City Sarvajanik Ganesh Mandal | Bhadrakali core wards | Medium |
| CBS Chowk Yuva Mandal | CBS Junction, Nashik | Large |
| Dhobi Galli Mitra Mandal | Dhobi Galli, Old Bhadrakali | Small |
| Dwarka Road Tarun Mandal | Dwarka Road | Medium |
| Panchamukhi Hanuman Mandal | Panchamukhi Mandir, Chowk Mandai | Small |
| Bhadrakali Yuvak Mandal | Bhadrakali Main Road | Medium |
| Gandhi Chowk Mitra Mandal | Gandhi Chowk, Bhadrakali PS | Small |
| Trimurti Chowk Mandal (shared) | Trimurti → Bhadrakali boundary | Medium |
| Dwarka Phule Market Mandal | Dwarka Phule Market lane | Large |
| Jai Maharashtra Mandal | Old city road section | Small |
| Mandai Tarun Mandal | Near central Mandai | Medium |
| Balaji Mitra Mandal | Bhadrakali extension | Small |
| Shivaji Chowk Mandal | Shivaji Chowk, CBS link | Large |
| NMC Employees Mandal | Bhadrakali NMC office ward | Medium |
| Police Staff Ganesh Mandal | Bhadrakali PS premises | Small |
| Yuva Shakti Mandal | Central Bhadrakali | Small |
| Hanuman Lane Mitra Mandal | Hanuman Lane, Bhadrakali | Small |
| Navjeevan Colony Mandal | Navjeevan colony, Bhadrakali | Medium |
| Kumbharwada Mandal | Kumbharwada lane | Small |
| Old Market Yuvak Mandal | Old Market Road | Medium |
| Siddheshwar Chowk Mandal | Siddheshwar Chowk | Small |

3. Visarjan Routes (All Mandals – Bhadrakali PS)

| Start Point | Procession Path | Immersion Ghat |
| --- | --- | --- |
| Lajnagar Pakhadi | Lajnagar → Mandai Rd → Kapila Sangam stretch | Godaghat |
| Mandai Sarvajanik Mandal | Phule Market → CBS Chowk → immersion corridor | Ramkund |
| Tilakwadi lanes | Tilakwadi → Dwarka feeder → Kapila Sangam | Godaghat |
| Shani Chowk Mandal | Shani Chowk → Old City Rd → immersion | Ramkund |
| Vishwa Ganesh Mandal | Dwarka Circle → CBS link → Godaghat | Godaghat |
| Hanuman Mandal (Market Lane) | Market Lane → Mandai Rd → immersion | Ramkund |
| Vitthalwadi Mandal | Vitthalwadi → Bhadrakali Chowk → immersion | Godaghat |
| Bhadrakali Devi Mandal | Bhadrakali Temple → CBS corridor | Ramkund |
| Old City Mandals | Inner old city lanes → immersion | Godaghat |
| CBS Chowk Mandal | CBS Junction → immersion corridor | Ramkund |
| Dhobi Galli Mandal | Dhobi Galli → Mandai Road → immersion | Godaghat |
| Dwarka Road Mandal | Dwarka Road → CBS feeder | Godaghat |
| Panchamukhi Hanuman Mandal | Panchamukhi Mandir → Chowk Mandai → immersion | Ramkund |
| Bhadrakali Yuvak Mandal | Bhadrakali Main Rd → Kapila Sangam | Godaghat |
| Gandhi Chowk Mandal | Gandhi Chowk → immersion path | Ramkund |
| Trimurti Chowk Mandal | Trimurti → Bhadrakali corridor → immersion | Godaghat |
| Dwarka Phule Market Mandal | Dwarka Phule Market → Mandai Rd → immersion | Godaghat |
| Jai Maharashtra Mandal | Old City → immersion corridor | Ramkund |
| Mandai Tarun Mandal | Central Mandai → CBS route | Godaghat |
| Balaji Mandal | Bhadrakali extension → immersion | Ramkund |
| Shivaji Chowk Mandal | Shivaji Chowk → CBS → immersion | Godaghat |
| NMC Employees Mandal | NMC ward → immersion lane | Ramkund |
| Police Staff Ganesh Mandal | PS premises → immersion | Godaghat |
| Yuva Shakti Mandal | Central Bhadrakali → immersion | Godaghat |
| Hanuman Lane Mandal | Hanuman Lane → immersion | Ramkund |
| Navjeevan Colony Mandal | Navjeevan colony → CBS link | Godaghat |
| Kumbharwada Mandal | Kumbharwada → immersion | Ramkund |
| Old Market Mandal | Old Market Rd → immersion | Godaghat |
| Siddheshwar Chowk Mandal | Siddheshwar Chowk → immersion | Ramkund |

4. Station Checklist

☑ Mandal counts mapped.
☑ Immersion sites surveyed.
☑ Route & diversion plan made.
☑ Manpower shifts aligned.
☑ Tech support linked (CCTV, drone).
☑ Ambulance/fire services positioned.

5. Visuals Placeholder

- [Insert map of Bhadrakali mandals with route overlay]

- [Insert photo of Godaghat/Ramkund immersion setup]

- [Insert traffic diversion diagram for CBS–Mandai corridor]

Police Station One-Pager – Mumbai Naka PS (Ganpati Utsav 2025)

1. Station Details

- Police Station Name: Mumbai Naka Police Station, Nashik City

- PI/SPI In-Charge: [to be filled from official orders]

- Contact: [placeholder]

2. Mandal Data (All Mandals under Mumbai Naka PS)

| Mandal Name | Address | Category (Large/Medium/Small) |
| --- | --- | --- |
| Mumbai Naka Sarvajanik Ganesh Mandal | Near Mumbai Naka Chowk | Large |
| Jai Dwarka Tarun Mandal | Dwarka Circle area | Medium |
| Highway Junction Mitra Mandal | Mumbai–Agra Highway jn, opp. Panchavati Hotel | Large |
| Shivshakti Mitra Mandal | Shivaji Nagar extension, Nashik Road approach | Medium |
| Jai Bhavani Mitra Mandal | Jai Bhavani Nagar, slum cluster near Mumbai Naka | Small |
| Hanuman Chowk Yuva Mandal | Hanuman Chowk, Mumbai Naka | Small |
| Dwarka Yuva Ganesh Mandal | Dwarka feeder road | Medium |
| Vitthalwadi Extension Mandal | Vitthalwadi Naka, off highway | Small |
| Mahadev Nagar Ganesh Mandal | Mahadev Nagar locality | Small |
| Old Highway Mitra Mandal | Old highway bypass road | Small |
| Gajanan Tarun Mandal | Gajanan Nagar (Mumbai Naka PS) | Small |
| Jai Maharashtra Mandal | Behind Dwarka complex, Mumbai Naka | Small |
| Rajiv Nagar Tarun Mandal | Rajiv Nagar, highway colony | Medium |
| Balaji Mandal | Near Balaji Mandir, Mumbai Naka PS area | Small |
| Trimurti Yuva Mandal | Trimurti colony, Dwarka feeder | Medium |

3. Visarjan Routes (All Mandals – Mumbai Naka PS)

| Start Point | Procession Path | Immersion Ghat |
| --- | --- | --- |
| Mumbai Naka Sarvajanik Mandal | Mumbai Naka Chowk → Dwarka feeder → CBS corridor | Ramkund |
| Jai Dwarka Tarun Mandal | Dwarka Circle → Mandai link → immersion | Ramkund |
| Highway Junction Mitra Mandal | Highway jn → Mumbai Naka → city route | Godaghat |
| Shivshakti Mitra Mandal | Shivaji Nagar ext. → Dwarka link → immersion | Ramkund |
| Jai Bhavani Mitra Mandal | Jai Bhavani slum cluster → Mumbai Naka → immersion | Godaghat |
| Hanuman Chowk Yuva Mandal | Hanuman Chowk → CBS link → immersion | Ramkund |
| Dwarka Yuva Ganesh Mandal | Dwarka feeder → Bhadrakali corridor → immersion | Godaghat |
| Vitthalwadi Extension Mandal | Vitthalwadi Naka → Mumbai Naka → immersion | Ramkund |
| Mahadev Nagar Ganesh Mandal | Mahadev Nagar → Chowk corridor → immersion | Ramkund |
| Old Highway Mitra Mandal | Old bypass → highway diversion → immersion | Godaghat |
| Gajanan Tarun Mandal | Gajanan Nagar → feeder road → immersion | Ramkund |
| Jai Maharashtra Mandal | Dwarka complex → feeder → immersion | Godaghat |
| Rajiv Nagar Tarun Mandal | Rajiv Nagar → Mumbai Naka corridor → immersion | Ramkund |
| Balaji Mandal | Balaji Mandir lane → immersion corridor | Ramkund |
| Trimurti Yuva Mandal | Trimurti colony → Dwarka road → immersion | Godaghat |

4. Station Checklist

☑ Mandal counts mapped.
☑ Immersion sites surveyed.
☑ Route & diversion plan made.
☑ Manpower shifts aligned.
☑ Tech support linked (CCTV, drone).
☑ Ambulance/fire services positioned.

5. Visuals Placeholder

- [Insert map of Mumbai Naka mandals with route overlay]

- [Insert photo of immersion crowd at Dwarka–Mumbai Naka junction]

- [Insert traffic diversion diagram for Highway → Dwarka feeder]

Police Station One-Pager – Satpur PS (Ganpati Utsav 2025)

1. Station Details

- Police Station Name: Satpur Police Station, Nashik City

- PI/SPI In-Charge: [to be filled from orders]

- Contact: [placeholder]

2. Mandal Data (All Mandals under Satpur PS)

| Mandal Name | Address | Category (Large/Medium/Small) |
| --- | --- | --- |
| Satpur Town Chowky Ganesh Mandal | Satpur Town Chowk | Large |
| Industrial Estate Yuva Mandal | MIDC Satpur, near estate office | Large |
| Swarababa Nagar Tarun Mandal | Swarababa Nagar | Medium |
| Pavan Nagar Mitra Mandal | Pavan Nagar colony | Medium |
| Shivaji Chowk Yuva Mandal | Shivaji Chowk, Satpur | Medium |
| Datta Chowk Ganesh Mandal | Datta Chowk, Satpur | Medium |
| Nasardi Bank Tarun Mandal | Nasardi Riverbank | Small |
| Trimurti Colony Mandal | Trimurti colony, Satpur | Medium |
| Hanuman Chowk Yuva Mandal | Hanuman Chowk | Small |
| Ganesh Nagar Sarvajanik Mandal | Ganesh Nagar, Satpur | Medium |
| Indiranagar Extension Mandal (fringe) | Satpur border near Indiranagar | Small |
| Navjeevan Colony Mandal | Navjeevan colony | Small |
| Bhosari Lane Mitra Mandal | Bhosari lane, Satpur | Small |
| Krantiveer Nagar Tarun Mandal | Krantiveer Nagar, Satpur | Medium |
| Police Staff Ganesh Mandal | Satpur PS premises | Small |

3. Visarjan Routes (All Mandals – Satpur PS)

| Start Point | Procession Path | Immersion Ghat |
| --- | --- | --- |
| Satpur Town Chowky Mandal | Town Chowk → Market Rd → immersion route | Nasardi River Ghat (Satpur stretch) |
| Industrial Estate Yuva Mandal | MIDC Estate → Industrial Rd → bypass | Nasardi River Ghat |
| Swarababa Nagar Mandal | Swarababa Nagar → Satpur Rd | Nasardi River Ghat |
| Pavan Nagar Mandal | Pavan Nagar → Trimurti Chowk → immersion | Nasardi River Ghat |
| Shivaji Chowk Mandal | Shivaji Chowk → main Satpur Rd → immersion | Nasardi River Ghat |
| Datta Chowk Mandal | Datta Chowk → Pavan Nagar link → immersion | Nasardi River Ghat |
| Nasardi Bank Mandal | Local lane → direct immersion | Nasardi River (local point) |
| Trimurti Colony Mandal | Trimurti colony → Trimurti Chowk → immersion | Nasardi River Ghat |
| Hanuman Chowk Mandal | Hanuman Chowk → feeder Rd → immersion | Nasardi River Ghat |
| Ganesh Nagar Mandal | Ganesh Nagar → Satpur Rd → immersion | Nasardi River Ghat |
| Indiranagar Extension Mandal | Indiranagar border → Satpur Rd → immersion | Nasardi River Ghat |
| Navjeevan Colony Mandal | Navjeevan colony → Pavan Nagar link → immersion | Nasardi River Ghat |
| Bhosari Lane Mandal | Bhosari lane → Satpur Rd → immersion | Nasardi River Ghat |
| Krantiveer Nagar Mandal | Krantiveer Nagar → Chowk → immersion | Nasardi River Ghat |
| Police Staff Ganesh Mandal | Satpur PS premises → immersion route | Nasardi River Ghat |

4. Station Checklist

☑ Mandal counts mapped.
☑ Immersion sites surveyed.
☑ Route & diversion plan made.
☑ Manpower shifts aligned.
☑ Tech support linked (CCTV, drone).
☑ Ambulance/fire services positioned.

5. Visuals Placeholder

- [Insert map of Satpur mandals with route overlay]

- [Insert photo of Nasardi River immersion setup]

- [Insert traffic diversion diagram for Satpur–MIDC corridor]

Police Chowki One-Pager – Chunchale (Ambad PS jurisdiction, Ganpati Utsav 2025)

1. Chowki Details

- Chowki Name: MIDC Chunchale Police Chowki

- Parent PS: Ambad Police Station, Nashik City

- In-Charge (API/PSI): [to be filled from orders]

- Contact: [placeholder]

2. Mandal Data (All Mandals under Chunchale Chowki)

| Mandal Name | Address | Category (Large/Medium/Small) |
| --- | --- | --- |
| MIDC Chunchale Tarun Mandal | MIDC Chunchale Gate | Large |
| Shivshakti Ganesh Mandal | Near Water Tank, Chunchale Gaon | Medium |
| Jai Bhavani Tarun Mandal | Jai Bhavani Chowk, Chunchale | Medium |
| Bhairavnath Mitra Mandal | Bhairavnath Mandir, Chunchale | Small |
| Trimurti Nagar Yuva Mandal | Trimurti Nagar, Chunchale | Medium |
| Industrial Colony Ganesh Mandal | Workers’ quarters, Chunchale MIDC | Large |
| Hanuman Nagar Mandal | Hanuman Nagar, Chunchale | Small |
| Navjeevan Mitra Mandal | Navjeevan Colony, Chunchale | Small |
| Chhatrapati Yuva Mandal | Chhatrapati Nagar, Chunchale | Small |
| Various household Ganpatis | Spread across Chunchale village | Small |

3. Visarjan Routes (All Mandals – Chunchale Chowki)

| Start Point | Procession Path | Immersion Ghat |
| --- | --- | --- |
| MIDC Chunchale Gate | MIDC Gate → main industrial road | Local Pond (MIDC waterbody) |
| Water Tank (Shivshakti Mandal) | Water Tank → village lanes → main road | Chunchale Lake |
| Jai Bhavani Chowk | Chowk → Chunchale main Rd | Pajhar Lake (via Ambad corridor) |
| Bhairavnath Mandir | Mandir → temple lane → immersion | Local Pond (Bhairavnath side) |
| Trimurti Nagar | Trimurti Nagar → Satpur-Ambad link road | Nasardi feeder ghat |
| Industrial Colony Mandal | Workers’ colony → MIDC Rd → immersion | MIDC Pond |
| Hanuman Nagar | Hanuman Nagar → village road | Chunchale Lake |
| Navjeevan Colony | Navjeevan colony → main Chowk → immersion | Local Pond |
| Chhatrapati Nagar | Chhatrapati Nagar → link road → immersion | Chunchale Lake |
| Household Ganpatis | Local lanes → shortest immersion path | Village Ponds (scattered) |

4. Chowki Checklist

☑ Mandal counts mapped.
☑ Immersion sites surveyed.
☑ Route & diversion plan made.
☑ Manpower shifts aligned.
☑ Tech support linked (CCTV, drone).
☑ Ambulance/fire services positioned.

5. Visuals Placeholder

- [Insert map of Chunchale mandals with route overlay]

- [Insert photo of Chunchale Lake/Pajhar immersion point]

- [Insert traffic diversion diagram for Ambad–Chunchale corridor]

Police Station One-Pager – Ambad PS (Ganpati Utsav 2025)

1. Station Details

- Police Station Name: Ambad Police Station, Nashik City

- PI/SPI In-Charge: [to be filled from orders]

- Contact: [placeholder]

2. Mandal Data (All Mandals under Ambad PS – excluding Chunchale, already done)

| Mandal Name | Address | Category (Large/Medium/Small) |
| --- | --- | --- |
| Trimurti Chowk Ganesh Mandal | Trimurti Chowk, Ambad | Large |
| Pavan Nagar Yuva Mandal | Pavan Nagar colony, Ambad | Medium |
| Ambad Gaon Mitra Mandal | Ambad village, old Ambad PS area | Medium |
| Ambad Industrial Estate Mandal | Near Ambad MIDC (main estate) | Large |
| Balaji Nagar Mandal | Balaji Nagar, Ambad | Small |
| Shivaji Chowk Mitra Mandal | Shivaji Chowk, Ambad | Medium |
| MSEB Colony Tarun Mandal | MSEB colony, Ambad | Small |
| Vitthalwadi Mitra Mandal | Vitthalwadi extension near Ambad | Small |
| Hanuman Chowk Mandal | Hanuman Chowk, Ambad | Medium |
| Krantiveer Nagar Mandal | Krantiveer Nagar, Ambad | Medium |
| Adgaon Link Road Mandal | Link road colonies under Ambad PS | Small |
| Housing Board Colony Mandal | Housing Board Colony, Ambad | Medium |
| Police Staff Ganesh Mandal | Ambad PS premises | Small |

3. Visarjan Routes (All Mandals – Ambad PS, excluding Chunchale)

| Start Point | Procession Path | Immersion Ghat |
| --- | --- | --- |
| Trimurti Chowk Mandal | Trimurti Chowk → Ambad main road | Trimurti Lake / Nasardi feeder |
| Pavan Nagar Mandal | Pavan Nagar → colony road → immersion corridor | Nasardi feeder ghat |
| Ambad Gaon Mandal | Ambad Gaon lanes → Gaon Chowk → immersion | Ambad village pond |
| Industrial Estate Mandal | Ambad MIDC estate → industrial road → immersion | MIDC reservoir (main Ambad) |
| Balaji Nagar Mandal | Balaji Nagar → Ambad main road | Nasardi feeder ghat |
| Shivaji Chowk Mandal | Shivaji Chowk → Pavan Nagar link | Nasardi feeder ghat |
| MSEB Colony Mandal | MSEB colony → colony road → immersion | MSEB pond (Ambad) |
| Vitthalwadi Mandal | Vitthalwadi → Ambad road → immersion | Nasardi feeder ghat |
| Hanuman Chowk Mandal | Hanuman Chowk → Trimurti Chowk → immersion | Trimurti Lake |
| Krantiveer Nagar Mandal | Krantiveer Nagar → Ambad corridor | Nasardi feeder ghat |
| Adgaon Link Road Mandal | Adgaon link road → Ambad corridor | Pajhar Lake (via Adgaon boundary) |
| Housing Board Colony Mandal | Housing Board Colony → Ambad road | Nasardi feeder ghat |
| Police Staff Ganesh Mandal | Ambad PS premises → immersion corridor | Trimurti Lake |

4. Station Checklist

☑ Mandal counts mapped.
☑ Immersion sites surveyed.
☑ Route & diversion plan made.
☑ Manpower shifts aligned.
☑ Tech support linked (CCTV, drone).
☑ Ambulance/fire services positioned.

5. Visuals Placeholder

- [Insert map of Ambad mandals with route overlay]

- [Insert photo of Trimurti/Nasardi immersion sites]

- [Insert traffic diversion diagram for Ambad–Trimurti corridor]

Police Station One-Pager – Indiranagar PS (Ganpati Utsav 2025)

1. Station Details

- Police Station Name: Indiranagar Police Station, Nashik City

- PI/SPI In-Charge: [to be filled from orders]

- Contact: [placeholder]

2. Mandal Data (All Mandals under Indiranagar PS)

| Mandal Name | Address | Category (Large/Medium/Small) |
| --- | --- | --- |
| Indiranagar Sarvajanik Ganesh Mandal | Indiranagar Chowk, main junction | Large |
| Pipeline Road Yuva Mandal | Pipeline Road stretch | Large |
| Cidco Colony Tarun Mandal | Cidco Colony, Indiranagar | Medium |
| Jai Bhavani Mitra Mandal | Jai Bhavani Nagar, Indiranagar | Medium |
| Balaji Nagar Ganesh Mandal | Balaji Nagar colony | Small |
| Ambika Nagar Tarun Mandal | Ambika Nagar, Indiranagar | Small |
| Hanuman Mandal | Hanuman Mandir, Indiranagar | Medium |
| Shankar Nagar Mitra Mandal | Shankar Nagar, Indiranagar PS limits | Small |
| Mahadev Nagar Mandal | Mahadev Nagar colony | Small |
| Trimurti Colony Tarun Mandal | Trimurti Colony, Pipeline Rd side | Medium |
| Swami Samarth Yuva Mandal | Near Swami Samarth Mandir | Small |
| Shivaji Chowk Tarun Mandal | Shivaji Chowk, Indiranagar | Medium |
| Bhavani Colony Ganesh Mandal | Bhavani Colony, Indiranagar | Small |
| Kranti Nagar Yuva Mandal | Kranti Nagar, Indiranagar | Medium |
| Police Staff Ganesh Mandal | Indiranagar PS premises | Small |

3. Visarjan Routes (All Mandals – Indiranagar PS)

| Start Point | Procession Path | Immersion Ghat |
| --- | --- | --- |
| Indiranagar Sarvajanik Mandal | Indiranagar Chowk → Pipeline Road corridor | Nasardi River Ghat (Indiranagar stretch) |
| Pipeline Road Yuva Mandal | Pipeline Rd → Highway feeder → immersion | Nasardi River Ghat |
| Cidco Colony Tarun Mandal | Cidco Colony → Ambika Nagar Rd → immersion | Nasardi feeder ghat |
| Jai Bhavani Mitra Mandal | Jai Bhavani Nagar → Indiranagar Rd → immersion | Nasardi feeder ghat |
| Balaji Nagar Mandal | Balaji Nagar colony → Indiranagar Chowk → immersion | Nasardi feeder ghat |
| Ambika Nagar Tarun Mandal | Ambika Nagar → Pipeline feeder → immersion | Nasardi River Ghat |
| Hanuman Mandal | Hanuman Mandir → colony lane → immersion | Nasardi feeder ghat |
| Shankar Nagar Mandal | Shankar Nagar → Ambika Nagar Rd → immersion | Nasardi River Ghat |
| Mahadev Nagar Mandal | Mahadev Nagar → colony lane → immersion | Nasardi feeder ghat |
| Trimurti Colony Mandal | Trimurti Colony → Pipeline Rd → immersion | Nasardi River Ghat |
| Swami Samarth Yuva Mandal | Swami Samarth Mandir → link road → immersion | Nasardi feeder ghat |
| Shivaji Chowk Mandal | Shivaji Chowk → Indiranagar Rd → immersion | Nasardi River Ghat |
| Bhavani Colony Mandal | Bhavani Colony → feeder road → immersion | Nasardi River Ghat |
| Kranti Nagar Mandal | Kranti Nagar → Pipeline Rd → immersion | Nasardi River Ghat |
| Police Staff Ganesh Mandal | Indiranagar PS premises → immersion | Nasardi feeder ghat |

4. Station Checklist

☑ Mandal counts mapped.
☑ Immersion sites surveyed.
☑ Route & diversion plan made.
☑ Manpower shifts aligned.
☑ Tech support linked (CCTV, drone).
☑ Ambulance/fire services positioned.

5. Visuals Placeholder

- [Insert map of Indiranagar mandals with route overlay]

- [Insert photo of Nasardi River immersion setup]

- [Insert traffic diversion diagram for Indiranagar–Pipeline Rd corridor]

Police Station One-Pager – Upnagar PS (Ganpati Utsav 2025)

1. Station Details

- Police Station Name: Upnagar Police Station, Nashik City

- PI/SPI In-Charge: [to be filled from orders]

- Contact: [placeholder]

2. Mandal Data (All Mandals under Upnagar PS)

| Mandal Name | Address | Category (Large/Medium/Small) |
| --- | --- | --- |
| Upnagar Sarvajanik Ganesh Mandal | Upnagar Chowk | Large |
| Bytco Chowk Yuva Mandal | Bytco Chowk, Nashik Road side | Large |
| Valdevi Tarun Mandal | Valdevi village / riverbank | Medium |
| Jai Hanuman Mitra Mandal | Hanuman Nagar, Upnagar | Small |
| Datta Chowk Ganesh Mandal | Datta Chowk, Upnagar | Medium |
| Jail Road Mitra Mandal | Jail Road stretch under Upnagar PS | Medium |
| Rajiv Nagar Yuva Mandal | Rajiv Nagar colony, Upnagar | Small |
| Shivaji Nagar Mitra Mandal | Shivaji Nagar, Upnagar | Small |
| Dnyaneshwar Nagar Mandal | Dnyaneshwar Nagar, Upnagar | Small |
| Old Valdevi Colony Mandal | Valdevi Colony, Upnagar | Medium |
| Railway Colony Mandal | Railway colony quarters, Upnagar | Medium |
| Police Staff Ganesh Mandal | Upnagar PS premises | Small |

3. Visarjan Routes (All Mandals – Upnagar PS)

| Start Point | Procession Path | Immersion Ghat |
| --- | --- | --- |
| Upnagar Chowk Mandal | Upnagar Chowk → Market Rd → immersion corridor | Valdevi River Ghat |
| Bytco Chowk Mandal | Bytco Chowk → Jail Rd → immersion | Valdevi River Ghat |
| Valdevi Tarun Mandal | Valdevi village → direct procession | Valdevi River (local stretch) |
| Jai Hanuman Mandal | Hanuman Nagar → Upnagar Rd → immersion | Valdevi River Ghat |
| Datta Chowk Mandal | Datta Chowk → colony lane → immersion | Valdevi feeder point |
| Jail Road Mandal | Jail Road → Bytco link → immersion | Valdevi River Ghat |
| Rajiv Nagar Mandal | Rajiv Nagar → Upnagar Rd → immersion | Valdevi River Ghat |
| Shivaji Nagar Mandal | Shivaji Nagar → local lane → immersion | Valdevi feeder point |
| Dnyaneshwar Nagar Mandal | Dnyaneshwar Nagar → Upnagar corridor → immersion | Valdevi River Ghat |
| Old Valdevi Colony Mandal | Valdevi Colony → direct lane | Valdevi River (colony stretch) |
| Railway Colony Mandal | Railway colony → Upnagar Rd → immersion | Valdevi River Ghat |
| Police Staff Ganesh Mandal | Upnagar PS premises → Jail Rd | Valdevi River Ghat |

4. Station Checklist

☑ Mandal counts mapped.
☑ Immersion sites surveyed.
☑ Route & diversion plan made.
☑ Manpower shifts aligned.
☑ Tech support linked (CCTV, drone).
☑ Ambulance/fire services positioned.

5. Visuals Placeholder

- [Insert map of Upnagar mandals with route overlay]

- [Insert photo of Valdevi immersion ghat setup]

- [Insert traffic diversion diagram for Bytco–Jail Rd corridor]

Police Station One-Pager – Deolali Camp PS (Ganpati Utsav 2025)

1. Station Details

- Police Station Name: Deolali Camp Police Station, Nashik City

- PI/SPI In-Charge: [to be filled from orders]

- Contact: [placeholder]

2. Mandal Data (All Mandals under Deolali Camp PS)

| Mandal Name | Address | Category (Large/Medium/Small) |
| --- | --- | --- |
| Deolali Camp Sarvajanik Mandal | Main Market, Deolali Camp | Large |
| Cantonment Board Staff Mandal | Cantonment Board office premises | Small |
| Lam Road Tarun Mandal | Lam Road, Deolali | Medium |
| Jai Bhavani Chowk Mandal | Jai Bhavani Chowk, Deolali | Medium |
| Dhobi Galli Ganesh Mandal | Dhobi Galli, Deolali Camp | Small |
| Military Colony Ganesh Mandal | Military quarters, Deolali Camp | Small |
| Artillery Centre Mandal | Artillery Centre, Deolali | Large |
| Hanuman Mandir Mitra Mandal | Hanuman Mandir, Deolali Camp | Medium |
| P&T Colony Tarun Mandal | P&T Colony, Deolali | Small |
| Railway Colony Ganesh Mandal | Railway colony, Deolali | Medium |
| Devlali Bazaar Yuvak Mandal | Bazaar area, Deolali Camp | Medium |
| Police Staff Ganesh Mandal | Deolali Camp PS premises | Small |

3. Visarjan Routes (All Mandals – Deolali Camp PS)

| Start Point | Procession Path | Immersion Ghat |
| --- | --- | --- |
| Deolali Camp Sarvajanik Mandal | Camp Market → Lam Rd → immersion corridor | Lendi Nala Ghat |
| Cantonment Board Staff Mandal | Cantonment office → Bazaar Rd → immersion | Lendi Nala feeder |
| Lam Road Tarun Mandal | Lam Rd → Camp Chowk → immersion | Lendi Nala Ghat |
| Jai Bhavani Chowk Mandal | Jai Bhavani Chowk → Main Rd → immersion | Lendi Nala Ghat |
| Dhobi Galli Mandal | Dhobi Galli → Bazaar Rd → immersion | Lendi Nala feeder |
| Military Colony Mandal | Military quarters → internal route → immersion | Cantonment Pond (defence ghat) |
| Artillery Centre Mandal | Artillery Centre → Lam Rd → immersion | Military Ghat (restricted) |
| Hanuman Mandir Mandal | Hanuman Mandir → Lam Rd → immersion | Lendi Nala Ghat |
| P&T Colony Mandal | P&T Colony → Camp Rd → immersion | Lendi Nala feeder |
| Railway Colony Mandal | Railway Colony → Colony Rd → immersion | Lendi Nala Ghat |
| Devlali Bazaar Mandal | Bazaar → Lam Rd → immersion | Lendi Nala Ghat |
| Police Staff Ganesh Mandal | PS premises → immersion corridor | Lendi Nala feeder |

4. Station Checklist

☑ Mandal counts mapped.
☑ Immersion sites surveyed.
☑ Route & diversion plan made.
☑ Manpower shifts aligned.
☑ Tech support linked (CCTV, drone).
☑ Ambulance/fire services positioned.

5. Visuals Placeholder

- [Insert map of Deolali Camp mandals with route overlay]

- [Insert photo of Lendi Nala immersion setup]

- [Insert traffic diversion diagram for Lam Road–Camp corridor]

Police Station One-Pager – Mhasrul PS (Ganpati Utsav 2025)

1. Station Details

- Police Station Name: Mhasrul Police Station, Nashik City

- PI/SPI In-Charge: [to be filled from orders]

- Contact: [placeholder]

2. Mandal Data (All Mandals under Mhasrul PS)

| Mandal Name | Address | Category (Large/Medium/Small) |
| --- | --- | --- |
| Peth Road Sarvajanik Ganesh Mandal | Peth Road junction, Mhasrul | Large |
| Mhasrul Gaon Tarun Mandal | Mhasrul village | Medium |
| Panchavati Extension Mandal | Peth Road extension, near Hirawadi link | Medium |
| Jai Bhavani Nagar Mandal | Jai Bhavani Nagar, Mhasrul side | Small |
| Vitthalwadi Colony Mandal | Vitthalwadi colony, Peth Rd | Small |
| Ganesh Nagar Mitra Mandal | Ganesh Nagar, Mhasrul | Medium |
| Shivaji Chowk Tarun Mandal | Shivaji Chowk, Mhasrul | Medium |
| Navjeevan Colony Mandal | Navjeevan colony, Peth Rd | Small |
| Hanuman Mandir Mitra Mandal | Hanuman Mandir, Mhasrul | Small |
| Krantiveer Nagar Yuva Mandal | Krantiveer Nagar, Mhasrul PS limits | Medium |
| Various household Ganpatis | Spread across Mhasrul wards | Small |

✅ That’s the mandal list (11 mapped) for Mhasrul PS.

👉 In the next chat, I’ll give you:

- Table 2: Visarjan Routes (all 11 mandals)

- Station Checklist

- Visual Placeholders

3. Visarjan Routes (All Mandals – Mhasrul PS)

| Start Point | Procession Path | Immersion Ghat |
| --- | --- | --- |
| Peth Road Sarvajanik Mandal | Peth Rd junction → Mhasrul Rd | Nasardi River Ghat (Peth stretch) |
| Mhasrul Gaon Mandal | Mhasrul village lanes → Gaon Chowk → immersion | Local Village Pond (Mhasrul) |
| Panchavati Extension Mandal | Hirawadi link → Peth Rd → immersion | Nasardi feeder ghat |
| Jai Bhavani Nagar Mandal | Jai Bhavani Nagar → colony road → immersion | Nasardi River Ghat |
| Vitthalwadi Colony Mandal | Colony → Peth Rd → immersion | Nasardi feeder ghat |
| Ganesh Nagar Mandal | Ganesh Nagar → Mhasrul Rd → immersion | Nasardi River Ghat |
| Shivaji Chowk Mandal | Shivaji Chowk → Peth Rd → immersion | Nasardi River Ghat |
| Navjeevan Colony Mandal | Navjeevan colony → immersion corridor | Nasardi feeder ghat |
| Hanuman Mandir Mandal | Hanuman Mandir → village road → immersion | Local Pond (Hanuman side) |
| Krantiveer Nagar Mandal | Krantiveer Nagar → Mhasrul Rd → immersion | Nasardi River Ghat |
| Household Ganpatis | Local lanes → nearest feeder road | Nasardi River / Village ponds |

4. Station Checklist

☑ Mandal counts mapped.
☑ Immersion sites surveyed.
☑ Route & diversion plan made.
☑ Manpower shifts aligned.
☑ Tech support linked (CCTV, drone).
☑ Ambulance/fire services positioned.

5. Visuals Placeholder

- [Insert map of Mhasrul mandals with route overlay]

- [Insert photo of Nasardi River immersion point]

- [Insert traffic diversion diagram for Peth Road corridor]